## Start Here
Getting Found in Oakville — six-month tracker
Working file for Luxury Beauty by Cleo R. Companion to seo-roadmap-6-month.docx
THE SHAPE OF IT
Runs | Monday 17 August 2026 to Sunday 14 February 2027. Twenty-six weeks, six months.
Right now | The rest of August is Google Business Profile and citations. Nothing else.
Week of Aug 24 | Website planning and design. Sitemap, wireframes, keyword-to-page map, copy outline.
Aug 31 | Design sign-off. This is the date the build waits on.
Sept 1 | Build starts. Launch target is the week of 5 October.
Field | Value | Where it gets decided
Business name (exact) | Luxury Beauty by Cleo R. | Use this spelling everywhere. No 'Med Spa', no 'Inc', no variations
Practitioner | Cleo Rukovo, NP | Nurse practitioner. Some healthcare directories list the person, not the practice
Address line 1 | 3060 Preserve Drive | Confirmed
Suite / unit |  | Waiting on the Allure conversation. This is what separates you from their listing
City | Oakville | Confirmed
Province | Ontario | Write 'Ontario' in full, or 'ON' — pick one and never mix them
Postal code | L6M 4L9 | Confirmed by Cleo, 21 Aug 2026. Listings showing L6M 0T9 are the error - verify against Canada Post before the mass correction
Country | Canada | Confirmed
Phone | (416) 294-0452 | One number, everywhere. A local 905 or 289 line beats the 416 mobile if you can get one
Email | Luxury.beautyaestheticz@gmail.com | One address. Currently split between crukovo@ and luxury.beautyaestheticz@
Website | https://luxurybeautybycleo.ca | Use the booking link until the site is live in October, then switch every listing
Booking URL | IG only | Needed before any directory that offers a booking button
Primary category | Medical Spa | Set on the Google profile first, then match it everywhere else
Secondary categories | Skin care clinic Weight loss service | Chosen to avoid colliding with Allure's listing
Short description (under 250 characters) |  | Names the town and the treatments. No prescription drug names, no benefit claims
Long description | Luxury Beauty by Cleo R. is a nurse practitioner-led medical spa in Oakville, Ontario, serving clients across Burlington, Mississauga, Milton and Halton Region. Our services include lip filler, dermal filler for volume loss, anti-wrinkle injections, jawline slimming, skin boosters for hydration and glow, dermaplaning, and electrolysis. Every visit begins with a one-on-one consultation so we can plan the right approach for your features and your goals. Our philosophy is simple: the right product, the right technique, and never more than you need. Every treatment is performed by Cleo Rukovo, NP. Book your consultation today. | Same rules. Write once, reuse everywhere
Hours — Monday | Closed | All seven days. 'Closed' is an answer; blank is not
Hours — Tuesday | Closed
Hours — Wednesday | Closed
Hours — Thursday | Closed
Hours — Friday | 10:00 AM–8:00 PM
Hours — Saturday | Closed
Hours — Sunday | Closed | The only hours on record anywhere today are Sunday 12 to 5
Year established | 2023
Service area | Oakville, Burlington, Milton, Mississauga, Glen Abbey, Joshua Creek, Bronte | Used where a directory asks for a service radius
Logo file | added | From design/brand
Cover photo | added
WHERE THINGS STAND
Project tasks
Not started
In progress
Blocked
Done
Overdue and not done
Percent complete
Daily slots done
Daily slots missed
Daily completion rate

## Daily Routine
The daily routine
Six slots. Five of them every weekday, the reel on Wednesday. This is the tab that explains the work; the Daily Log is the tab you tick.
Slot | Task | Cadence | What it involves | Owner | Logged on | Status
EVERY DAY
1 | Google Business Profile post | Every weekday | One post a day. Rotate the five types across the week: treatment spotlight, FAQ or myth, before and after, offer or availability, practice update. Copy and images come from the content calendar. Every post ends with the booking link. | Cleo | GBP Posts tab | In progress
2 | Instagram post or stories | Every weekday | A feed post on the calendar days, two or three stories on the rest. Location-tag Oakville every time, write the alt text every time, use the local hashtag set. | Cleo | Content calendar | In progress
3 | Reel | Once a week — Wednesday | One reel a week, filmed and cut in the Wednesday batch block. Rotate the four types across the month: a treatment in fifteen seconds, a myth-buster, behind the scenes in the room, a patient question answered to camera. Reuse each cut as a story and a GBP video. | Cleo | Daily Log tab | In progress
4 | On-page optimisation | Every weekday | Before launch: keyword-to-page mapping, drafting title tags and meta descriptions, writing page copy for the build. After launch: one page improved a day on rotation — title tag, H1, internal links, image alt text, schema, thin content topped up. | Agency | Tasks tab | Not started
5 | Review ask | Every weekday | The WhatsApp message inside 24 hours to every patient seen that day, and a reply to any review that landed. This is the single highest-return thing in the plan. | Cleo | Reviews tab | Not applicable
6 | Citations | Daily to week 4, then weekly | One directory a day. The Citations tab first ,the listings that exist and are wrong , then the Local Citations build list, where there is no listing at all. Once both are clean, one a week to keep them that way. Name, address and phone identical everywhere, no exceptions. | Agency | Citations + Local Citations | Not started
EVERY WEEK
Mon | Google profile insights and rank check | Weekly | Calls, views and direction requests for the week. Where the map pack has you for the three target terms. Two minutes, written down, every Monday. | Agency | Metrics tab | In progress
Wed | Content and reel batch | Weekly | Film the reel, batch the week's GBP posts and Instagram captions so the daily slots are a five-minute publish rather than a blank page. | Both | Content calendar | Not started
Fri | Log the week | Weekly | Fill in the week's numbers, close out the Tasks tab, flag anything blocked. Ad review every second Friday. | Agency | Tasks tab | Not started
EVERY MONTH
| Fill the Metrics tab | Monthly | Every number for the month end. Compare against the baseline column, not against last month. | Agency | Metrics tab | Not started
| Refresh the Google profile | Monthly | Services list, questions and answers, photo set. A profile that never changes stops earning. | Agency | Tasks tab | Not started
| Competitor and query check | Monthly | What the three named competitors are doing, and which queries Search Console shows you sitting just outside the first page for. | Agency | Metrics tab | Not started
| Review the month's best work | Monthly | The posts that drove profile visits and the pages that drove sessions. More of those next month. | Both | Metrics tab | Not started
The reel is once a week, on Wednesday, filmed in the Wednesday batch block. Do not try to do one a day.
Before the site is live, the on-page slot is preparation: keyword mapping, title tags, meta descriptions, page copy.
From launch onward it is one real page improved a day, on rotation, so no page goes six months untouched.
Compliance applies to Google posts exactly as it applies to Instagram. Nothing names a prescription drug.

## Daily Log
Daily log
One row per weekday, 17 August 2026 to 12 February 2027. Mark each slot Done, Missed or N/A. The reel column is only live on Wednesdays. |  |  |  |  | Slots done |  | Slots missed |  | Completion
|  |  | GBP posts |  | Reels |  | Review asks |  | Days logged
Date | Day | Week | GBP post | IG post / story | Reel | On-page | Review ask | Citation | Done | Notes
AUGUST 2026
2026-08-17 | Mon | W1 | Done | Done | Done | N/A | N/A
2026-08-18 | Tue | W1 | Done | Done | Done | N/A | N/A
2026-08-19 | Wed | W1 | Done | Done | Done | N/A | N/A
2026-08-20 | Thu | W1 | Done | Done | N/A | N/A | N/A
2026-08-21 | Fri | W1 |  |  | N/A
2026-08-24 | Mon | W2 |  |  | N/A
2026-08-25 | Tue | W2 |  |  | N/A
2026-08-26 | Wed | W2
2026-08-27 | Thu | W2 |  |  | N/A
2026-08-28 | Fri | W2 |  |  | N/A
2026-08-31 | Mon | W3 |  |  | N/A
SEPTEMBER 2026
2026-09-01 | Tue | W3 |  |  | N/A
2026-09-02 | Wed | W3
2026-09-03 | Thu | W3 |  |  | N/A
2026-09-04 | Fri | W3 |  |  | N/A
2026-09-07 | Mon | W4 |  |  | N/A
2026-09-08 | Tue | W4 |  |  | N/A
2026-09-09 | Wed | W4
2026-09-10 | Thu | W4 |  |  | N/A
2026-09-11 | Fri | W4 |  |  | N/A
2026-09-14 | Mon | W5 |  |  | N/A
2026-09-15 | Tue | W5 |  |  | N/A
2026-09-16 | Wed | W5
2026-09-17 | Thu | W5 |  |  | N/A
2026-09-18 | Fri | W5 |  |  | N/A
2026-09-21 | Mon | W6 |  |  | N/A
2026-09-22 | Tue | W6 |  |  | N/A
2026-09-23 | Wed | W6
2026-09-24 | Thu | W6 |  |  | N/A
2026-09-25 | Fri | W6 |  |  | N/A
2026-09-28 | Mon | W7 |  |  | N/A
2026-09-29 | Tue | W7 |  |  | N/A
2026-09-30 | Wed | W7
OCTOBER 2026
2026-10-01 | Thu | W7 |  |  | N/A
2026-10-02 | Fri | W7 |  |  | N/A
2026-10-05 | Mon | W8 |  |  | N/A
2026-10-06 | Tue | W8 |  |  | N/A
2026-10-07 | Wed | W8
2026-10-08 | Thu | W8 |  |  | N/A
2026-10-09 | Fri | W8 |  |  | N/A
2026-10-12 | Mon | W9 |  |  | N/A
2026-10-13 | Tue | W9 |  |  | N/A
2026-10-14 | Wed | W9
2026-10-15 | Thu | W9 |  |  | N/A
2026-10-16 | Fri | W9 |  |  | N/A
2026-10-19 | Mon | W10 |  |  | N/A
2026-10-20 | Tue | W10 |  |  | N/A
2026-10-21 | Wed | W10
2026-10-22 | Thu | W10 |  |  | N/A
2026-10-23 | Fri | W10 |  |  | N/A
2026-10-26 | Mon | W11 |  |  | N/A
2026-10-27 | Tue | W11 |  |  | N/A
2026-10-28 | Wed | W11
2026-10-29 | Thu | W11 |  |  | N/A
2026-10-30 | Fri | W11 |  |  | N/A
NOVEMBER 2026
2026-11-02 | Mon | W12 |  |  | N/A
2026-11-03 | Tue | W12 |  |  | N/A
2026-11-04 | Wed | W12
2026-11-05 | Thu | W12 |  |  | N/A
2026-11-06 | Fri | W12 |  |  | N/A
2026-11-09 | Mon | W13 |  |  | N/A
2026-11-10 | Tue | W13 |  |  | N/A
2026-11-11 | Wed | W13
2026-11-12 | Thu | W13 |  |  | N/A
2026-11-13 | Fri | W13 |  |  | N/A
2026-11-16 | Mon | W14 |  |  | N/A
2026-11-17 | Tue | W14 |  |  | N/A
2026-11-18 | Wed | W14
2026-11-19 | Thu | W14 |  |  | N/A
2026-11-20 | Fri | W14 |  |  | N/A
2026-11-23 | Mon | W15 |  |  | N/A
2026-11-24 | Tue | W15 |  |  | N/A
2026-11-25 | Wed | W15
2026-11-26 | Thu | W15 |  |  | N/A
2026-11-27 | Fri | W15 |  |  | N/A
2026-11-30 | Mon | W16 |  |  | N/A
DECEMBER 2026
2026-12-01 | Tue | W16 |  |  | N/A
2026-12-02 | Wed | W16
2026-12-03 | Thu | W16 |  |  | N/A
2026-12-04 | Fri | W16 |  |  | N/A
2026-12-07 | Mon | W17 |  |  | N/A
2026-12-08 | Tue | W17 |  |  | N/A
2026-12-09 | Wed | W17
2026-12-10 | Thu | W17 |  |  | N/A
2026-12-11 | Fri | W17 |  |  | N/A
2026-12-14 | Mon | W18 |  |  | N/A
2026-12-15 | Tue | W18 |  |  | N/A
2026-12-16 | Wed | W18
2026-12-17 | Thu | W18 |  |  | N/A
2026-12-18 | Fri | W18 |  |  | N/A
2026-12-21 | Mon | W19 |  |  | N/A
2026-12-22 | Tue | W19 |  |  | N/A
2026-12-23 | Wed | W19
2026-12-24 | Thu | W19 |  |  | N/A
2026-12-25 | Fri | W19 |  |  | N/A
2026-12-28 | Mon | W20 |  |  | N/A
2026-12-29 | Tue | W20 |  |  | N/A
2026-12-30 | Wed | W20
2026-12-31 | Thu | W20 |  |  | N/A
JANUARY 2027
2027-01-01 | Fri | W20 |  |  | N/A
2027-01-04 | Mon | W21 |  |  | N/A
2027-01-05 | Tue | W21 |  |  | N/A
2027-01-06 | Wed | W21
2027-01-07 | Thu | W21 |  |  | N/A
2027-01-08 | Fri | W21 |  |  | N/A
2027-01-11 | Mon | W22 |  |  | N/A
2027-01-12 | Tue | W22 |  |  | N/A
2027-01-13 | Wed | W22
2027-01-14 | Thu | W22 |  |  | N/A
2027-01-15 | Fri | W22 |  |  | N/A
2027-01-18 | Mon | W23 |  |  | N/A
2027-01-19 | Tue | W23 |  |  | N/A
2027-01-20 | Wed | W23
2027-01-21 | Thu | W23 |  |  | N/A
2027-01-22 | Fri | W23 |  |  | N/A
2027-01-25 | Mon | W24 |  |  | N/A
2027-01-26 | Tue | W24 |  |  | N/A
2027-01-27 | Wed | W24
2027-01-28 | Thu | W24 |  |  | N/A
2027-01-29 | Fri | W24 |  |  | N/A
FEBRUARY 2027
2027-02-01 | Mon | W25 |  |  | N/A
2027-02-02 | Tue | W25 |  |  | N/A
2027-02-03 | Wed | W25
2027-02-04 | Thu | W25 |  |  | N/A
2027-02-05 | Fri | W25 |  |  | N/A
2027-02-08 | Mon | W26 |  |  | N/A
2027-02-09 | Tue | W26 |  |  | N/A
2027-02-10 | Wed | W26
2027-02-11 | Thu | W26 |  |  | N/A
2027-02-12 | Fri | W26 |  |  | N/A

## 90-Day Overview
The first 90 days
17 August to 15 November 2026. Week 13 closes day 90. Counts pull live from the Tasks tab this is where you look at progress, that is where you change it.
THE THREE CHECKPOINTS — what has to be true, and by when
Checkpoint | Date | What must be true by then |  |  |  | On track | Notes
Day 30 | 2026-09-15 | Google profile claimed, verified, complete and posting daily. All 17 existing listings corrected AND verified at L6M 4L9. Design signed off, build two weeks in. Review asks going out every day.
Day 60 | 2026-10-15 | Site live. Every treatment page published, Search Console verified, sitemap submitted. Every citation repointed at the live URL. Ads running on three audiences.
Day 90 | 2026-11-15 | Eight to ten new reviews. Visible in the map pack for 'botox oakville' (480 searches a month) and 'lip filler oakville'. First two or three articles live and indexed. Local link building started. Note: 'nurse injector oakville' has no measurable search volume - own it, but do not measure by it.
WEEK BY WEEK — the first 90 days
Week | Dates | Phase | The one thing that matters | Tasks due | Done | Progress | Status | Notes
W1 | 17 Aug – 23 Aug | Foundation | Claim and verify the Google profile. Nothing else can start until it is settled |  |  |  | Done
W2 | 24 Aug – 30 Aug | Foundation | Design sign-off Friday 28 August, and the citation corrections begin |  |  |  | Not started
W3 | 31 Aug – 06 Sep | Build | Design signed off Monday. BUILD STARTS 1 SEPTEMBER |  |  |  | Not started
W4 | 07 Sep – 13 Sep | Build | Home and contact complete in staging. Citations verified, not just corrected |  |  |  | Not started
W5 | 14 Sep – 20 Sep | Build | First four treatment pages. The review ask is now a daily habit |  |  |  | Not started
W6 | 21 Sep – 27 Sep | Build | Second pair of treatment pages. Ad audiences built |  |  |  | Not started
W7 | 28 Sep – 04 Oct | Build | Last treatment pages and the area page. Mobile speed pass |  |  |  | Not started
W8 | 05 Oct – 11 Oct | Launch | LAUNCH WEEK. Search Console verified, sitemap in, every listing repointed |  |  |  | Not started
W9 | 12 Oct – 18 Oct | Index and optimise | Confirm every page is indexed. First local link submissions |  |  |  | Not started
W10 | 19 Oct – 25 Oct | Index and optimise | On-page pass on the four highest-intent pages. First article |  |  |  | Not started
W11 | 26 Oct – 01 Nov | Index and optimise | Fix whatever Search Console flags. Second article |  |  |  | Not started
W12 | 02 Nov – 08 Nov | Index and optimise | Month three review and a rank check against the baseline |  |  |  | Not started
W13 | 09 Nov – 15 Nov | Review | DAY 90. Full read against the week-one baseline |  |  |  | Not started
AFTER DAY 90 — the second half
Month | Dates | Theme
Month 4 | 9 Nov – 6 Dec | Depth on the pages that earn. Thin pages expanded, gallery, articles four to six
Month 5 | 7 Dec – 10 Jan | Hold the cadence through the holidays. Reduced posting, never stopped posting
Month 6 | 11 Jan – 14 Feb | Compound it. Near-miss queries, technical audit, the six-month report
Week 13 is both the day-90 review and the first week of month four. It appears in two places on purpose.
THE DATES THAT DO NOT MOVE
Date | What | Why it matters |  |  |  | Status | Notes
2026-08-31 | Design sign-off | The build gate. Everything after it moves one-for-one |  |  |  | Not started
2026-09-01 | Build starts | Hosting, DNS, platform, page scaffolding |  |  |  | Not started
2026-10-05 | Launch week begins | Site live by Sunday 11 October |  |  |  | Not started
2026-11-15 | Day 90 review | Every number against the week-one baseline |  |  |  | Not started

## Tasks
ID | Month | Week | Due | Area | Task | Owner | Cadence | Priority | Status | Date done | Notes / blockers
3 | Month 1 | W1 | 2026-08-23 | Google profile | Claim and verify the Google Business Profile | Agency | One-off | High | Done
5 | Month 1 | W1 | 2026-08-23 | Google profile | Set real opening hours on GBP for every day of the week | Agency | One-off | High | Done
6 | Month 1 | W1 | 2026-08-23 | Google profile | Choose the primary GBP category | Agency | One-off | High | Done
7 | Month 1 | W1 | 2026-08-23 | Google profile | Choose secondary categories that avoid colliding with Allure's listing | Agency | One-off | High | Done
8 | Month 1 | W1 | 2026-08-23 | Google profile | Replace the dead website link on GBP with the booking link until the site is live | Agency | One-off | High | Done
9 | Month 1 | W1 | 2026-08-23 | Google profile | Upload real photos to GBP: treatment room, you, the space | Both | One-off | High | In progress
10 | Month 1 | W1 | 2026-08-23 | Citations | Decide on one email address and one phone number to use everywhere | Cleo | One-off | High | In progress
11 | Month 1 | W1 | 2026-08-23 | Citations | Audit every listing that mentions the practice and record the wrong NAP on the Citations tab | Agency | One-off | High | Not started
12 | Month 1 | W1 | 2026-08-23 | Citations | Fill in THE RECORD on the Local Citations tab: one name, one address, one phone, one email | Both | One-off | High | Not started
13 | Month 1 | W1 | 2026-08-23 | Daily routine | Start the daily routine: GBP post, Instagram, on-page, review ask, citation | Cleo | Daily | High | Done
14 | Month 1 | W1 | 2026-08-23 | Daily routine | Agree who does which daily slot and put it in the calendar | Both | One-off | High | Done
15 | Month 1 | W1 | 2026-08-23 | Measurement | Record the baseline: 12 reviews, 5.0 average, GBP calls, views and direction requests | Agency | One-off | High | Not started
16 | Month 1 | W1 | 2026-08-23 | Measurement | Send us your real opening hours for every day of the week | Cleo | One-off | High | Not started
17 | Month 1 | W1 | 2026-08-23 | Measurement | Name the three competitors you want to be measured against | Cleo | One-off | Medium | Not started
23 | Month 1 | W2 | 2026-08-30 | Citations | Check which directories on the Local Citations build list are still live and still free | Agency | One-off | Medium | Not started
24 | Month 1 | W2 | 2026-08-30 | Website | PLANNING WEEK: agree the sitemap and the full page inventory | Both | One-off | High | Not started
25 | Month 1 | W2 | 2026-08-30 | Website | Build the keyword-to-page map so every page has one job | Agency | One-off | High | Not started
26 | Month 1 | W2 | 2026-08-30 | Website | Wireframe the home page, the contact page and the treatment page template | Agency | One-off | High | Not started
27 | Month 1 | W2 | 2026-08-30 | Website | Pull the brand kit — colours, type, logo — from design/brand | Agency | One-off | Medium | Not started
28 | Month 1 | W2 | 2026-08-30 | Website | Send the domain registrar login for luxurybeautybycleo.ca | Cleo | One-off | High | Not started
29 | Month 1 | W2 | 2026-08-30 | Website | Send the treatment list with current pricing | Cleo | One-off | High | Not started
30 | Month 1 | W2 | 2026-08-30 | Website | DESIGN REVIEW with Cleo. Sign-off due Friday 28 August | Both | One-off | High | Not started
31 | Month 1 | W2 | 2026-08-30 | Instagram | Rewrite the Instagram name field to read 'Cleo ¦ Nurse Injector Oakville' | Agency | One-off | High | Not started
32 | Month 1 | W2 | 2026-08-30 | Instagram | Rewrite the Instagram bio to name the town and the treatments | Agency | One-off | High | Not started
33 | Month 1 | W2 | 2026-08-30 | Instagram | Fix the link in bio so it no longer points at the dead domain | Agency | One-off | High | Not started
34 | Month 1 | W2 | 2026-08-30 | Instagram | Start location-tagging Oakville on every post | Cleo | Ongoing | High | Not started
35 | Month 1 | W2 | 2026-08-30 | Reviews | Write the WhatsApp review-ask message | Agency | One-off | High | Not started
36 | Month 1 | W2 | 2026-08-30 | Reviews | Reply to all 12 existing reviews | Cleo | One-off | Medium | Not started
37 | Month 1 | W3 | 2026-09-06 | Website | DESIGN SIGN-OFF DUE Monday 31 August | Cleo | One-off | High | Not started
38 | Month 1 | W3 | 2026-09-06 | Website | BUILD STARTS 1 SEPTEMBER: hosting sorted, DNS pointed, platform set up | Agency | One-off | High | Not started
39 | Month 1 | W3 | 2026-09-06 | Website | Scaffold the page structure agreed in planning | Agency | One-off | High | Not started
40 | Month 1 | W3 | 2026-09-06 | Website | Write the home page copy and get it approved | Both | One-off | High | Not started
41 | Month 1 | W3 | 2026-09-06 | Website | Write the contact page copy with the corrected NAP and hours | Agency | One-off | High | Not started
42 | Month 1 | W3 | 2026-09-06 | Citations | Correct postal code to L6M 4L9 on Apple Maps | Agency | One-off | Medium | Not started
43 | Month 1 | W3 | 2026-09-06 | Citations | Correct postal code to L6M 4L9 on Bing Places | Agency | One-off | Medium | Not started
44 | Month 1 | W3 | 2026-09-06 | Citations | Correct postal code to L6M 4L9 on RateMDs | Agency | One-off | Low | Not started
45 | Month 1 | W3 | 2026-09-06 | Citations | Build the Oakville and Halton local citations from the build list | Agency | One-off | High | Not started
46 | Month 1 | W3 | 2026-09-06 | Google profile | Fill out the GBP services list with a plain description of each treatment | Agency | One-off | Medium | Not started
47 | Month 1 | W3 | 2026-09-06 | Google profile | Add a working booking link to GBP | Agency | One-off | High | Not started
48 | Month 1 | W3 | 2026-09-06 | Reviews | Start sending the review ask within 24 hours of every appointment | Cleo | Daily | High | Not started
49 | Month 1 | W3 | 2026-09-06 | Compliance | Confirm the signed before-and-after consent form is on file | Cleo | One-off | High | Not started
50 | Month 1 | W4 | 2026-09-13 | Website | Home and contact pages complete in staging: NAP, hours, booking link, schema | Agency | One-off | High | Not started
51 | Month 1 | W4 | 2026-09-13 | Website | LocalBusiness and Service schema on every page built so far | Agency | One-off | High | Not started
52 | Month 1 | W4 | 2026-09-13 | Website | Title tags and meta descriptions for the home and contact pages | Agency | One-off | High | Not started
53 | Month 1 | W4 | 2026-09-13 | Citations | Correct postal code to L6M 4L9 on the Canadian chamber directories | Agency | One-off | Low | Not started
54 | Month 1 | W4 | 2026-09-13 | Citations | Claim any listing about the practice that is not under your control | Agency | One-off | Medium | Not started
55 | Month 1 | W4 | 2026-09-13 | Citations | Verify every corrected listing now shows identical name, address and phone | Agency | One-off | High | Not started
56 | Month 1 | W4 | 2026-09-13 | Citations | Build the healthcare and aesthetics citations, the NPAO listing included | Agency | One-off | Medium | Not started
57 | Month 1 | W4 | 2026-09-13 | Citations | Check the College of Nurses public register entry is correct as it stands | Agency | One-off | Medium | Not started
58 | Month 1 | W4 | 2026-09-13 | Google profile | Seed the GBP questions section with real questions and answers | Both | One-off | Medium | Not started
59 | Month 1 | W4 | 2026-09-13 | Google profile | Post to GBP every weekday from the content calendar | Cleo | Daily | High | Not started
60 | Month 1 | W4 | 2026-09-13 | Compliance | Compliance pass on the 21 briefs naming Botox or Dysport in client-facing copy | Agency | One-off | High | Not started
61 | Month 1 | W4 | 2026-09-13 | Compliance | Compliance rules apply to GBP posts too — brief Cleo on what cannot be named | Agency | One-off | High | Not started
62 | Month 1 | W4 | 2026-09-13 | Measurement | Set up the analytics property ready for launch | Agency | One-off | Medium | Not started
63 | Month 1 | W4 | 2026-09-13 | Ads | Send us your current monthly Instagram and Google ad spend | Cleo | One-off | High | Not started
64 | Month 2 | W5 | 2026-09-20 | Website | Build the treatment pages: lip filler, dermal filler and facial balancing | Agency | One-off | High | Not started
65 | Month 2 | W5 | 2026-09-20 | Website | Write the copy for those pages and confirm every claim is one you can stand behind | Both | One-off | High | Not started
66 | Month 2 | W5 | 2026-09-20 | Website | Title tag, meta description and H1 on every treatment page built | Agency | One-off | High | Not started
67 | Month 2 | W5 | 2026-09-20 | Citations | Build the Canadian directory, maps and social profile citations | Agency | One-off | Low | Not started
68 | Month 2 | W5 | 2026-09-20 | Reviews | Design and print the QR review card for the treatment room | Agency | One-off | Medium | Not started
69 | Month 2 | W5 | 2026-09-20 | Reviews | Reply to every new review within two days | Cleo | Ongoing | Medium | Not started
70 | Month 2 | W5 | 2026-09-20 | Instagram | Switch to locally weighted hashtag sets, clear of prescription brand names | Agency | One-off | Medium | Not started
71 | Month 2 | W5 | 2026-09-20 | Instagram | Write alt text on every new post | Cleo | Ongoing | Medium | Not started
72 | Month 2 | W5 | 2026-09-20 | Content | Publish one reel every Wednesday | Cleo | Weekly | High | Not started
73 | Month 2 | W6 | 2026-09-27 | Website | Build the treatment pages: anti-wrinkle injections and skin boosters | Agency | One-off | High | Not started
74 | Month 2 | W6 | 2026-09-27 | Website | Internal linking pass across every page built so far | Agency | One-off | Medium | Not started
75 | Month 2 | W6 | 2026-09-27 | Website | Compress every image and write alt text across the site | Agency | One-off | Medium | Not started
76 | Month 2 | W6 | 2026-09-27 | Instagram | Reorganise Highlights by treatment | Agency | One-off | Medium | Not started
77 | Month 2 | W6 | 2026-09-27 | Ads | Build the local radius audience, 15km around Oakville | Agency | One-off | High | Not started
78 | Month 2 | W6 | 2026-09-27 | Ads | Build the 30-day engagement retargeting audience | Agency | One-off | High | Not started
79 | Month 2 | W6 | 2026-09-27 | Reviews | Check the ask against the review target and adjust it if it is lagging | Agency | Monthly | High | Not started
80 | Month 2 | W7 | 2026-10-04 | Website | Build the treatment pages: dermaplaning, electrolysis and Belkyra | Agency | One-off | High | Not started
81 | Month 2 | W7 | 2026-10-04 | Website | Build the Oakville and surrounding-area page | Agency | One-off | Medium | Not started
82 | Month 2 | W7 | 2026-10-04 | Website | Mobile speed pass | Agency | One-off | Medium | Not started
83 | Month 2 | W7 | 2026-10-04 | Ads | Export the patient list from the booking system for the lookalike audience | Cleo | One-off | Medium | Not started
84 | Month 2 | W7 | 2026-10-04 | Ads | Build the lookalike audience | Agency | One-off | Medium | Not started
85 | Month 2 | W7 | 2026-10-04 | Ads | Launch three or four ad creatives pulled from existing carousels | Agency | One-off | High | Not started
86 | Month 2 | W8 | 2026-10-11 | Website | Final content and compliance review of every page before launch | Both | One-off | High | Not started
87 | Month 2 | W8 | 2026-10-11 | Website | LAUNCH: site live, Search Console verified, sitemap submitted, analytics running | Agency | One-off | High | Not started
88 | Month 2 | W8 | 2026-10-11 | Website | Repoint the GBP website field at the live site | Agency | One-off | High | Not started
89 | Month 2 | W8 | 2026-10-11 | Citations | Update every directory listing to the new website URL | Agency | One-off | Medium | Not started
90 | Month 2 | W8 | 2026-10-11 | Citations | Update every citation built before launch from the booking link to the live site URL | Agency | One-off | High | Not started
91 | Month 2 | W8 | 2026-10-11 | Instagram | Update the link in bio to the live site | Agency | One-off | High | Not started
92 | Month 2 | W8 | 2026-10-11 | Measurement | Confirm Search Console and analytics are both recording on the live domain | Agency | One-off | High | Not started
93 | Month 2 | W8 | 2026-10-11 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
94 | Month 3 | W9 | 2026-10-18 | Website | Confirm every page is indexed in Search Console and fix what is not | Agency | One-off | High | Not started
95 | Month 3 | W9 | 2026-10-18 | Website | On-page pass on the home page: title, H1, opening copy, internal links | Agency | One-off | High | Not started
96 | Month 3 | W9 | 2026-10-18 | Local links | Submit to the Oakville business directories | Agency | One-off | Medium | Not started
97 | Month 3 | W9 | 2026-10-18 | Local links | Ask Allure about a cross-link between the two businesses | Cleo | One-off | Low | Not started
98 | Month 3 | W9 | 2026-10-18 | Measurement | First post-launch read on Search Console impressions and queries | Agency | One-off | Medium | Not started
99 | Month 3 | W10 | 2026-10-25 | Website | On-page pass on the four highest-intent treatment pages | Agency | One-off | High | Not started
100 | Month 3 | W10 | 2026-10-25 | Website | Add FAQ blocks with FAQ schema to every treatment page | Agency | One-off | Medium | Not started
101 | Month 3 | W10 | 2026-10-25 | Content | Write the first question-intent article and link it to its treatment page | Agency | One-off | Medium | Not started
102 | Month 3 | W10 | 2026-10-25 | Local links | Approach Halton-area partners for mentions and links | Agency | One-off | Medium | Not started
103 | Month 3 | W10 | 2026-10-25 | Google profile | Add the weight-loss service entry to GBP ahead of the launch | Agency | One-off | Medium | Not started
104 | Month 3 | W11 | 2026-11-01 | Website | Fix whatever Search Console flags: coverage, mobile usability, core web vitals | Agency | One-off | High | Not started
105 | Month 3 | W11 | 2026-11-01 | Content | Write the second question-intent article | Agency | One-off | Medium | Not started
106 | Month 3 | W11 | 2026-11-01 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
107 | Month 3 | W11 | 2026-11-01 | Reviews | Check the ask conversion rate and rewrite the message if it is under 30 per cent | Agency | One-off | High | Not started
108 | Month 3 | W12 | 2026-11-08 | Measurement | Month three review: every number against the week-one baseline | Agency | Monthly | High | Not started
109 | Month 3 | W12 | 2026-11-08 | Measurement | Rank check on the map pack terms and the page terms | Agency | Monthly | High | Not started
110 | Month 3 | W12 | 2026-11-08 | Content | Write the third question-intent article | Agency | One-off | Medium | Not started
111 | Month 3 | W12 | 2026-11-08 | Local links | Chase every unanswered link approach | Agency | One-off | Low | Not started
112 | Month 4 | W13 | 2026-11-15 | Website | Build the weight-loss pre-launch page | Agency | One-off | Medium | Not started
113 | Month 4 | W13 | 2026-11-15 | Content | Write the fourth article from the questions you get asked in consults | Agency | One-off | Medium | Not started
114 | Month 4 | W13 | 2026-11-15 | Instagram | Review which posts drove profile visits and rebalance the calendar | Agency | Monthly | Medium | Not started
115 | Month 4 | W13 | 2026-11-15 | Google profile | Refresh the GBP photo set with new room and result photos | Both | One-off | Medium | Not started
116 | Month 4 | W14 | 2026-11-22 | Website | Expand the thin treatment pages: pricing ranges, aftercare, who it is not for | Agency | One-off | High | Not started
117 | Month 4 | W14 | 2026-11-22 | Local links | Sponsor or join one Oakville community listing or event | Cleo | One-off | Medium | Not started
118 | Month 4 | W14 | 2026-11-22 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
119 | Month 4 | W14 | 2026-11-22 | Content | Write the fifth article | Agency | One-off | Medium | Not started
120 | Month 4 | W15 | 2026-11-29 | Website | Add a before-and-after gallery page using consent-cleared photos only | Agency | One-off | Medium | Not started
121 | Month 4 | W15 | 2026-11-29 | Compliance | Compliance pass on the gallery page before it goes live | Agency | One-off | High | Not started
122 | Month 4 | W15 | 2026-11-29 | Google profile | Post the December holiday hours to GBP | Agency | One-off | Medium | Not started
123 | Month 4 | W15 | 2026-11-29 | Reviews | Holiday review push: ask every patient seen in November | Cleo | One-off | High | Not started
124 | Month 4 | W16 | 2026-12-06 | Measurement | Month four review: compare Search Console queries month on month | Agency | Monthly | High | Not started
125 | Month 4 | W16 | 2026-12-06 | Website | Internal linking pass now that the articles exist | Agency | One-off | Medium | Not started
126 | Month 4 | W16 | 2026-12-06 | Content | Write the sixth article | Agency | One-off | Medium | Not started
127 | Month 5 | W17 | 2026-12-13 | Google profile | Set the holiday opening hours on GBP for December and January | Agency | One-off | High | Not started
128 | Month 5 | W17 | 2026-12-13 | Instagram | Plan the December gift-card and holiday content | Agency | One-off | Medium | Not started
129 | Month 5 | W17 | 2026-12-13 | Website | Add a gift-card or holiday offer block to the home page | Agency | One-off | Medium | Not started
130 | Month 5 | W18 | 2026-12-20 | Ads | Holiday campaign: reallocate budget to the gift-card creative | Agency | Fortnightly | High | Not started
131 | Month 5 | W18 | 2026-12-20 | Content | Write the seventh article | Agency | One-off | Medium | Not started
132 | Month 5 | W18 | 2026-12-20 | Citations | Quarterly citation audit across both the Citations and Local Citations tabs | Agency | One-off | Medium | Not started
133 | Month 5 | W19 | 2026-12-27 | Instagram | Reduced holiday cadence: stories only, one reel, but keep GBP posting daily | Cleo | One-off | Medium | Not started
134 | Month 5 | W19 | 2026-12-27 | Google profile | Confirm the holiday hours showing on Google are actually correct | Agency | One-off | High | Not started
135 | Month 5 | W20 | 2027-01-03 | Measurement | Year-end read: reviews, map pack positions, sessions and bookings | Agency | Monthly | High | Not started
136 | Month 5 | W20 | 2027-01-03 | Content | Plan the January content calendar | Agency | One-off | Medium | Not started
137 | Month 5 | W21 | 2027-01-10 | Website | January on-page sprint: refresh every title tag and meta description | Agency | One-off | High | Not started
138 | Month 5 | W21 | 2027-01-10 | Instagram | Back to full cadence with new-year treatment content | Cleo | One-off | High | Not started
139 | Month 5 | W21 | 2027-01-10 | Reviews | New-year review push | Cleo | One-off | High | Not started
140 | Month 5 | W21 | 2027-01-10 | Ads | Relaunch the standard campaign set after the holiday creative | Agency | Fortnightly | High | Not started
141 | Month 6 | W22 | 2027-01-17 | Website | Build the full weight-loss treatment page now the service is live | Agency | One-off | High | Not started
142 | Month 6 | W22 | 2027-01-17 | Content | Write the eighth article | Agency | One-off | Medium | Not started
143 | Month 6 | W22 | 2027-01-17 | Local links | Second round of local link approaches | Agency | One-off | Medium | Not started
144 | Month 6 | W23 | 2027-01-24 | Measurement | Full query review: find every term you rank between 5 and 15 for | Agency | One-off | High | Not started
145 | Month 6 | W23 | 2027-01-24 | Website | Optimise the pages behind those near-miss terms | Agency | One-off | High | Not started
146 | Month 6 | W23 | 2027-01-24 | Website | Content refresh on the three lowest-performing pages | Agency | One-off | Medium | Not started
147 | Month 6 | W24 | 2027-01-31 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
148 | Month 6 | W24 | 2027-01-31 | Reviews | Check the review count against the six-month target | Agency | Monthly | High | Not started
149 | Month 6 | W24 | 2027-01-31 | Google profile | Refresh the GBP services list and the questions section | Agency | One-off | Medium | Not started
150 | Month 6 | W25 | 2027-02-07 | Measurement | Full review of every number against the week-one baseline | Agency | One-off | High | Not started
151 | Month 6 | W25 | 2027-02-07 | Website | Technical audit: speed, schema, broken links, redirects | Agency | One-off | High | Not started
152 | Month 6 | W25 | 2027-02-07 | Citations | Final citation audit for the engagement | Agency | One-off | Medium | Not started
153 | Month 6 | W26 | 2027-02-14 | Measurement | Write the six-month report | Agency | One-off | High | Not started
154 | Month 6 | W26 | 2027-02-14 | Measurement | Write the recommendation for the next six months | Agency | One-off | High | Not started
155 | Month 6 | W26 | 2027-02-14 | Website | Hand over the site documentation and every login | Agency | One-off | High | Not started
156 | Month 1 | W1 | 2026-08-23 | Citations | Verify the postal code L6M 4L9 against a Canada Post address lookup and the lease, then lock THE RECORD | Cleo | One-off | High | Not started |  | This reverses the correction instruction on 17 listings. Confirm once, in writing, before anything is submitted
157 | Month 2 | W6 | 2026-09-20 | Website | Decide whether to add laser hair removal as a service - 480 searches a month at KD 9, and it is not offered today | Cleo | One-off | Medium | Not started |  | The single biggest untapped term in the Target Keywords tab. A service decision, not an SEO one
158 | Month 2 | W3 | 2026-09-06 | Website | Sign off the keyword-to-page map on the Site Structure tab before the build starts | Both | One-off | High | Not started |  | One page per keyword. Merging lip filler and dermal filler would cannibalise both
159 | Month 2 | W7 | 2026-09-27 | Measurement | Create the Semrush project for luxurybeautybycleo.ca | Agency | One-off | High | Not started |  | No Semrush project exists today. Position Tracking and Site Audit both require one before either can run
160 | Month 2 | W7 | 2026-09-27 | Measurement | Configure Semrush Position Tracking: keywords from the Target Keywords tab, geo-targeted to Oakville ON, mobile and desktop | Agency | One-off | High | Not started |  | Track Tier 1 and Tier 2 only. Tier 4 has no measurable volume and would just add noise
161 | Month 2 | W7 | 2026-09-27 | Website | Install the Microsoft Clarity tag sitewide and verify it is recording, before launch | Agency | One-off | High | Not started |  | Must be live on launch day or the first weeks of visitor behaviour are lost and cannot be recovered
162 | Month 3 | W8 | 2026-10-04 | Website | Link Microsoft Clarity to Google Analytics and set the booking-link click as a tracked event | Agency | One-off | High | Not started |  | Without the event, heatmaps show where people click but not whether they booked
163 | Month 3 | W9 | 2026-10-11 | Measurement | Enable Semrush Site Audit, run the first crawl at launch and record the health score as the baseline | Agency | One-off | High | Not started |  | Needs a resolving site - cannot run before launch
164 | Month 3 | W9 | 2026-10-11 | Measurement | Log Semrush visibility and position changes to the Metrics tab | Agency | Weekly | Medium | Not started |  | Slots into the existing Monday insights block on the Daily Routine tab
165 | Month 3 | W9 | 2026-10-11 | Measurement | Review Clarity heatmaps and session recordings for the week, and log what you found on the Heatmap Tracking tab | Agency | Weekly | Medium | Not started |  | Weekly for the first month after launch, then monthly. A finding with no logged change is not a finding
166 | Month 3 | W10 | 2026-10-18 | Measurement | Log the Site Audit health score and new issue count to the Metrics tab | Agency | Monthly | Medium | Not started
167 | Month 3 | W10 | 2026-10-18 | Content | Confirm the blog pillar order on the Blog Pillars tab - Cost & Value ships first | Both | One-off | Medium | Not started |  | Lowest difficulty and highest commercial intent of the four pillars

## Site Build
Website build timeline
Approved, full build. Real dates, not weeks-from-approval. Everything after 31 August slips one-for-one if the design sign-off slips.
When | What we do | What we need from Cleo | Status | Date done | Notes
Aug 24 - 28 | Planning and design: sitemap, page inventory, wireframes for home, contact and the treatment template, keyword-to-page map, brand kit pulled from design/brand | Registrar login, treatment list with current pricing, photos of the room, a headshot, logo files | Not started
Aug 31 | Design sign-off. This is the gate — nothing is built before it clears | Sign off the wireframes and the look, in writing | Not started
Sep 1 - 6 | BUILD STARTS. Hosting sorted, DNS pointed at the new site, platform set up, page structure scaffolded | Nothing. This week is ours | Not started
Sep 7 - 13 | Home and contact complete in staging: corrected address at L6M 4L9, real hours, booking link, LocalBusiness and Service schema, title tags and meta descriptions | Read the home page copy and approve it | Not started
Sep 14 - 27 | Treatment pages: lip filler, dermal filler and facial balancing, anti-wrinkle injections, skin boosters. Internal linking, image compression, alt text | Read the copy and confirm every claim is one you can stand behind | Not started
Sep 28 - Oct 4 | Remaining treatment pages: dermaplaning, electrolysis, Belkyra. The Oakville and surrounding-area page. Mobile speed pass | Nothing. This week is ours | Not started
Oct 5 - 11 | LAUNCH. Search Console verified, sitemap submitted, analytics running, GBP website field repointed, every citation updated to the new URL | Final sign-off before it goes live | Not started
Oct 12 - Nov 8 | Indexing and on-page. Fix whatever Search Console flags, FAQ schema on the treatment pages, the first three question-intent articles | The questions you get asked most in consults | Not started
Nov 9 - Feb 14 | Depth. Weight-loss page, before-and-after gallery, five more articles, near-miss query optimisation, technical audit, handover | Consent-cleared photos as they come, and the consult questions | Not started

## Target Keywords
Target keywords
All volume, difficulty and CPC figures below are live Semrush data, Canada database, pulled 21 August 2026. Nothing here is estimated. Re-pull each quarter.
HOW TO READ THIS
Volume is monthly Canadian searches. KD is Semrush keyword difficulty, 0 to 100 - under 15 is reachable for a new site, over 40 needs authority you will not have this year.
Tier 1 is what the treatment pages are built to win. Tier 2 is adjacent and area terms. Tier 3 feeds the blog. Tier 4 is worth owning but will never show up in a traffic report.
One keyword, one page. Two pages chasing the same term split the signal and neither ranks.
TIER 1 - MONEY TERMS. These are what the treatment pages are built to win.
Nine of the eleven sit at KD 25 or below. This is a soft local SERP - Reddit outranks most clinics for botox oakville.
Keyword | Volume /mo | KD | CPC (CAD) | Intent | Target page | Channel | Current rank | Last checked | Notes
botox oakville | 480 | 25 | 0 | Commercial | /anti-wrinkle-injections/ | Map pack + organic |  |  | The biggest local prize. Reddit ranks #2 for this today and oakvillederm #1 - the SERP is soft.
lip filler oakville | 170 | 7 | 2.45 | Commercial | /lip-filler/ | Organic |  |  | KD 7. The roadmap called this 'competitive, first page not guaranteed'. The data says otherwise - take it.
med spa oakville | 140 | 29 | 1.35 | Commercial | / | Map pack + organic |  |  | Hardest of the tier. Home page term, won on reviews and profile strength as much as copy.
electrolysis oakville | 140 | 11 | 0.81 | Commercial | /electrolysis/ | Organic |  |  | Confirmed low competition, as the roadmap assumed. Real volume behind it.
lip injections oakville | 110 | 5 | 2.03 | Transactional | /lip-filler/ | Organic |  |  | Transactional intent. Secondary H2 on the lip filler page - NOT its own page, it would cannibalise.
dermal filler oakville | 90 | 5 | 4.8 | Commercial | /dermal-filler-facial-balancing/ | Organic |  |  | Lowest difficulty with real volume, and the highest CPC in the local set - the most commercially valuable term here.
best botox oakville | 70 | 16 | 1.84 | Commercial | /anti-wrinkle-injections/ | Organic |  |  | Review-driven. Will not move until the review count climbs; revisit month 3.
botox oakville ontario | 50 | 0 | 0 | Commercial | /anti-wrinkle-injections/ | Organic |  |  | KD 0. Free win - one H2 and a mention in the meta description.
dermaplaning oakville | 40 | 0 | 1.16 | Commercial | /dermaplaning/ | Organic |  |  | KD 0. Should rank within weeks of launch.
medspa oakville | 30 | 0 | 1.36 | Commercial | / | Organic |  |  | Spelling variant of med spa oakville. Same page, no separate treatment.
belkyra oakville | 10 | 0 | 0 | Commercial | /belkyra/ | Organic |  |  | Tiny, but uncontested. Worth a page because nobody else has one.
TIER 2 - ADJACENT SERVICES AND SURROUNDING AREA
Near-me terms are won by the Google profile, never by a page. Burlington and Mississauga wait until Oakville is won.
Keyword | Volume /mo | KD | CPC (CAD) | Intent | Target page | Channel | Current rank | Last checked | Notes
laser hair removal oakville | 480 | 9 | 1.76 | Commercial | -- not a service today -- | Decision needed |  |  | THE BIGGEST UNTAPPED TERM IN THIS SHEET. 480/mo at KD 9 and Cleo does not offer it. Decide whether to add the service.
facial oakville | 320 | 9 | 1.13 | Commercial | /dermaplaning/ | Organic |  |  | Dermaplaning is a facial. Worth an H2 and an internal link - 8x the volume of dermaplaning oakville.
skin clinic oakville | 140 | 32 | 1.26 | Commercial | / | Organic |  |  | Home page secondary term.
weight loss clinic oakville | 70 | 38 | 4.81 | Commercial | /weight-loss/ | Organic |  |  | Highest CPC in the whole set at $4.81, and the hardest KD. Month 4 pre-launch page, month 6 full page.
nurse injector toronto | 50 | 0 | 0 | Commercial | /about-np-cleo/ | Organic |  |  | KD 0. 'nurse injector' has volume in Toronto but none in Oakville - see Tier 4.
aesthetic clinic oakville | 40 | 0 | 0 | Commercial | / | Organic |  |  | KD 0.
nurse injector near me | 30 | 0 | 1.68 | Commercial | GBP | Map pack only |  |  | Won by the Google profile, not the site.
cosmetic clinic oakville | 30 | 0 | 1.39 | Commercial | / | Organic |  |  | KD 0.
filler oakville | 20 | 0 | 0 | Commercial | /dermal-filler-facial-balancing/ | Organic |  |  | Head-term variant.
injectables oakville | 10 | 0 | 0 | Commercial | / | Organic |  |  | Small, but KD 0.
botox near me | 6600 | 24 | 2.25 | Commercial | GBP | Map pack only |  |  | Huge, but national and won only by the Google profile. Never a page target.
med spa near me | 880 | 24 | 1.45 | Commercial | GBP | Map pack only |  |  | Depends entirely on resolving the Allure same-address filtering.
lip filler near me | 880 | 11 | 1.61 | Commercial | GBP | Map pack only |  |  | Profile term, not a page term.
botox burlington | 390 | 37 | 2.62 | Commercial | /oakville-and-area/ | Month 5+ |  |  | Do not chase before Oakville is won. KD 37 is the hardest local term in the set.
lip filler burlington | 90 | 9 | 2.04 | Commercial | /oakville-and-area/ | Month 5+ |  |  | KD 9 - the easiest of the Burlington set.
med spa burlington | 70 | 28 | 1.68 | Commercial | /oakville-and-area/ | Month 5+
botox mississauga | 480 | 17 | 0 | Commercial | -- watch only -- | Watch |  |  | Skin Vitality territory (10,350 keywords, 33,870 visits/mo). Outside the 15km service area. Do not chase.
lip filler mississauga | 260 | 18 | 1.76 | Commercial | -- watch only -- | Watch |  |  | Outside service area. Watch only.
TIER 3 - QUESTION TERMS. These feed the blog, not the treatment pages.
Every row maps to a pillar and an article on the Blog Pillars tab. Ordered by volume.
Keyword | Volume /mo | KD | CPC (CAD) | Intent | Pillar | Article | Current rank | Last checked | Notes
how long does lip filler last | 1000 | 15 | 0.22 | Informational | Longevity & Aftercare | /blog/how-long-does-lip-filler-last/
botox aftercare | 1000 | 32 | 0.5 | Informational | Longevity & Aftercare | /blog/aftercare-anti-wrinkle-injections/
what is dermaplaning | 880 | 23 | 0.03 | Informational | Treatment Explainers | /blog/what-is-dermaplaning/
what is a dermaplane | 880 | 24 | 0.03 | Informational | Treatment Explainers | /blog/what-is-dermaplaning/
electrolysis vs laser hair removal | 480 | 28 | 0.24 | Informational | Treatment Explainers | /blog/electrolysis-vs-laser-hair-removal/
baby botox | 480 | 17 | 1.2 | Informational | First-timer, Safety & Candidacy | /blog/baby-botox-and-preventative-treatment/
how much is lip filler | 390 | 11 | 0.72 | Informational | Cost & Value | /blog/how-much-does-lip-filler-cost-in-oakville/
lip filler aftercare | 320 | 14 | 0.05 | Informational | Longevity & Aftercare | /blog/lip-filler-aftercare/
how much does lip filler cost | 260 | 15 | 0.7 | Informational | Cost & Value | /blog/how-much-does-lip-filler-cost-in-oakville/
how to dermaplane | 210 | 27 | 0.02 | Informational | Treatment Explainers | /blog/what-is-dermaplaning/
is dermaplaning good for skin | 210 | 35 | 0.03 | Informational | Treatment Explainers | /blog/what-is-dermaplaning/
preventative botox | 210 | 45 | 1.39 | Informational | First-timer, Safety & Candidacy | /blog/baby-botox-and-preventative-treatment/
what is electrolysis hair removal | 170 | 43 | 0.02 | Informational | Treatment Explainers | /blog/electrolysis-vs-laser-hair-removal/
how often should you dermaplane | 140 | 19 | 0.03 | Informational | Treatment Explainers | /blog/what-is-dermaplaning/
lip filler swelling | 140 | 28 | 0 | Informational | Longevity & Aftercare | /blog/lip-filler-aftercare/
does lip filler hurt | 110 | 7 | 0.02 | Informational | First-timer, Safety & Candidacy | /blog/what-to-expect-first-filler-appointment/
can you get lip filler while pregnant | 110 | 10 | 0 | Informational | First-timer, Safety & Candidacy | /blog/who-is-not-a-candidate/
how much is lip filler in canada | 110 | 5 | 0.66 | Informational | Cost & Value | /blog/how-much-does-lip-filler-cost-in-oakville/
how much does botox cost in ontario | 90 | 4 | 0 | Informational | Cost & Value | /blog/what-anti-wrinkle-treatment-costs-in-ontario/
botox cost canada | 90 | 11 | 0 | Informational | Cost & Value | /blog/what-anti-wrinkle-treatment-costs-in-ontario/
what are skin boosters | 90 | 23 | 0 | Informational | Treatment Explainers | /blog/what-are-skin-boosters/
what is a skin booster | 90 | 23 | 0 | Informational | Treatment Explainers | /blog/what-are-skin-boosters/
how to know if lip filler has gone wrong | 90 | 21 | 0 | Informational | First-timer, Safety & Candidacy | /blog/who-is-not-a-candidate/
how long does dermaplaning last | 90 | 15 | 0.03 | Informational | Longevity & Aftercare | /blog/what-is-dermaplaning/
how often can you dermaplane | 90 | 11 | 0.03 | Informational | Treatment Explainers | /blog/what-is-dermaplaning/
what not to do after lip filler | 70 | 18 | 0 | Informational | Longevity & Aftercare | /blog/lip-filler-aftercare/
how long does lip filler swelling last | 70 | 0 | 0 | Informational | Longevity & Aftercare | /blog/lip-filler-aftercare/
TIER 4 - OWN IT, BUT DO NOT MEASURE BY IT
Every term here returned NO ROW in Semrush - below the volume floor. They cost nothing to include on a page and they convert when someone does search them. They will not move a traffic number.
Keyword | Volume /mo | KD | CPC (CAD) | Intent | Target page | Channel | Current rank | Last checked | Notes
nurse injector oakville | no data | - | - | Commercial | /about-np-cleo/ | Secondary H2 |  |  | NO ROW IN SEMRUSH - below the volume floor. The roadmap names this the top expected win and the Day 90 checkpoint rests on it. Own it (zero competition, perfect intent, good for GBP) but never measure success by it.
skin booster oakville | no data | - | - | Commercial | /skin-boosters/ | Secondary H2 |  |  | No measurable local volume. The national term 'what are skin boosters' (90/mo) is the real route in.
anti wrinkle injections oakville | no data | - | - | Commercial | /anti-wrinkle-injections/ | Secondary H2 |  |  | No measurable volume - Canadians search the brand name, not the category. Compliance limits how far you can lean on the brand.
facial balancing oakville | no data | - | - | Commercial | /dermal-filler-facial-balancing/ | Secondary H2 |  |  | No measurable volume. Industry vocabulary, not patient vocabulary.
cheek filler oakville | no data | - | - | Commercial | /dermal-filler-facial-balancing/ | Secondary H2 |  |  | No measurable volume, though competitive density is 0.92 - clinics bid on it. H2 only.
botox glen abbey | no data | - | - | Commercial | /oakville-and-area/ | Secondary H2 |  |  | No measurable volume. Neighbourhood terms do not register; the area page covers it.
botox milton ontario | no data | - | - | Commercial | /oakville-and-area/ | Secondary H2 |  |  | No measurable volume.
wrinkle treatment oakville | no data | - | - | Commercial | /anti-wrinkle-injections/ | Secondary H2 |  |  | No measurable volume.
botox specials oakville | no data | - | - | Commercial | -- none -- | Secondary H2 |  |  | No measurable volume, and discount framing sits badly with CNO advertising standards.
DO NOT CHASE - and why, so nobody re-adds them in month 4
Keyword | Volume /mo | KD | Reason to leave it alone
what is botox | 2400 | 94 | KD 94. Owned by Wikipedia, Mayo Clinic and Health Canada. Unwinnable, and no commercial intent.
what is in botox | 1300 | 87 | KD 87. Same story.
what is the botox | 1300 | 86 | KD 86. Malformed query, no intent.
what is botox made of | 590 | 85 | KD 85. Pharmacology, not a clinic topic.
is botox bad for you | 590 | 64 | KD 64, and ranking for it invites a reputational frame you cannot control.
can botox cause cancer | 390 | 44 | Do not touch. Answering it in advertising copy is a Health Canada and CNO risk with no upside.
what is hair botox | 590 | 32 | A hair smoothing treatment - entirely different product. Wrong traffic.
how long does botox last | 1900 | 41 | KD 41 with big volume. Tempting, but leave it until month 5 once the blog has authority.
did millie bobby brown get lip filler | 320 | 32 | Celebrity gossip. No commercial intent, off-brand.
is lip filler haram | 70 | 14 | Low KD but religiously framed. Not a clinic's place to answer.

## Site Structure
Site structure
The keyword-to-page map the Site Build tab calls for in the Aug 24 - 28 planning week. Sign this off before the build starts on 1 September. Volumes are Semrush CA, 21 Aug 2026.
THE RULES THIS MAP FOLLOWS
One keyword, one page. lip filler oakville and dermal filler oakville are separate pages - merging them splits the signal and neither ranks.
Title tags are 60 characters or fewer, meta descriptions 155 or fewer, so Google shows them whole.
Every treatment page links to contact and to at least one article. Every article links back to its treatment page. That internal linking is what makes the blog worth writing.
Depth 0 is the home page, 1 is one click from it, 2 is two. Nothing a patient needs should sit deeper than 2.
CORE PAGES
URL path | Page type | Depth | Primary keyword | Vol /mo | KD | Secondary keywords | Title tag (max 60) | Meta description (max 155) | H1 | Schema | Linked from | Links to | Build week | Status
/ | Home | 0 | med spa oakville | 140 | 29 | medspa oakville; skin clinic oakville; aesthetic clinic oakville; cosmetic clinic oakville; injectables oakville | Med Spa in Oakville ¦ Luxury Beauty by Cleo R. | Nurse-practitioner-led injectables and skin treatments in Oakville. Lip filler, dermal filler, skin boosters and dermaplaning. Book with Cleo. | Injectables and skin treatments in Oakville | MedicalBusiness + LocalBusiness | - | Every treatment page, contact, about | Sep 7 - 13 | Not started
/contact/ | Contact | 1 | med spa oakville | 140 | 29 | directions; hours; booking | Contact ¦ Luxury Beauty by Cleo R. Oakville | 3060 Preserve Drive, Oakville ON L6M 4L9. Opening hours, directions and booking for Luxury Beauty by Cleo R. | Find us in Oakville | LocalBusiness | Home, every treatment page | Booking link | Sep 7 - 13 | Not started
/about-np-cleo/ | About | 1 | nurse injector oakville | no data | - | nurse injector toronto (50); nurse injector near me (30) | About Cleo Rukovo, NP ¦ Nurse Injector in Oakville | Cleo Rukovo is a nurse practitioner and injector in Oakville. Training, approach and what a first appointment looks like. | Meet Cleo Rukovo, NP | Person + MedicalBusiness | Home, every treatment page | Contact, treatment pages | Sep 7 - 13 | Not started
/lip-filler/ | Treatment | 1 | lip filler oakville | 170 | 7 | lip injections oakville (110, KD 5); filler oakville (20) | Lip Filler in Oakville ¦ Luxury Beauty by Cleo R. | Lip filler in Oakville with nurse practitioner Cleo Rukovo. What it involves, how long it lasts, and what it costs. | Lip filler in Oakville | Service + FAQPage | Home, /results/, blog articles | Contact, /results/, /blog/how-long-does-lip-filler-last/ | Sep 14 - 27 | Not started
/dermal-filler-facial-balancing/ | Treatment | 1 | dermal filler oakville | 90 | 5 | cheek filler oakville; facial balancing oakville; filler oakville (20) | Dermal Filler & Facial Balancing ¦ Oakville | Dermal filler and facial balancing in Oakville. A nurse practitioner's approach to proportion rather than volume. | Dermal filler and facial balancing | Service + FAQPage | Home, /lip-filler/ | Contact, /results/ | Sep 14 - 27 | Not started
/anti-wrinkle-injections/ | Treatment | 1 | botox oakville | 480 | 25 | best botox oakville (70, KD 16); botox oakville ontario (50, KD 0) | Anti-Wrinkle Injections in Oakville ¦ Cleo R. | Anti-wrinkle injections in Oakville with a nurse practitioner. How treatment works, what to expect, and how long results last. | Anti-wrinkle injections in Oakville | Service + FAQPage | Home, blog articles | Contact, /blog/baby-botox-and-preventative-treatment/ | Sep 14 - 27 | Not started
/skin-boosters/ | Treatment | 1 | skin booster oakville | no data | - | what are skin boosters (90, national); what is a skin booster (90) | Skin Boosters in Oakville ¦ Luxury Beauty by Cleo R. | Skin boosters in Oakville. What they are, who they suit, and how they differ from filler. With nurse practitioner Cleo Rukovo. | Skin boosters in Oakville | Service + FAQPage | Home, /blog/what-are-skin-boosters/ | Contact | Sep 14 - 27 | Not started
/dermaplaning/ | Treatment | 1 | dermaplaning oakville | 40 | 0 | facial oakville (320, KD 9) - 8x the volume, same page | Dermaplaning in Oakville ¦ Luxury Beauty by Cleo R. | Dermaplaning in Oakville. A gentle resurfacing facial that removes dead skin and fine hair. Book with Cleo Rukovo, NP. | Dermaplaning in Oakville | Service + FAQPage | Home, /blog/what-is-dermaplaning/ | Contact | Sep 28 - Oct 4 | Not started
/electrolysis/ | Treatment | 1 | electrolysis oakville | 140 | 11 | electrolysis vs laser hair removal (480, KD 28) | Electrolysis in Oakville ¦ Luxury Beauty by Cleo R. | Permanent hair removal by electrolysis in Oakville. How it compares to laser, what a session involves, and how many you need. | Electrolysis in Oakville | Service + FAQPage | Home, /blog/electrolysis-vs-laser-hair-removal/ | Contact | Sep 28 - Oct 4 | Not started
/belkyra/ | Treatment | 1 | belkyra oakville | 10 | 0 | - | Belkyra in Oakville ¦ Luxury Beauty by Cleo R. | Belkyra treatment in Oakville for fullness under the chin. What it involves and how many sessions are typical. | Belkyra in Oakville | Service + FAQPage | Home | Contact | Sep 28 - Oct 4 | Not started
/oakville-and-area/ | Area | 1 | botox burlington | 390 | 37 | lip filler burlington (90, KD 9); med spa burlington (70, KD 28); botox glen abbey | Serving Oakville, Burlington, Milton & Mississauga | Luxury Beauty by Cleo R. serves Oakville, Burlington, Milton, Mississauga, Glen Abbey, Joshua Creek and Bronte. | Where we serve | LocalBusiness | Home, contact | Contact, treatment pages | Sep 28 - Oct 4 | Not started
/results/ | Gallery | 1 | lip filler before and after | 1300 | - | botox before and after (1900). Difficulty for both not pulled - Semrush API units exhausted | Before & After ¦ Luxury Beauty by Cleo R. Oakville | Real before-and-after results from Luxury Beauty by Cleo R. in Oakville. Every photo published with written consent. | Before and after | ImageGallery | Home, every treatment page | Treatment pages, contact | Nov 9 - Feb 14 | Not started
/weight-loss/ | Treatment | 1 | weight loss clinic oakville | 70 | 38 | - | Weight Loss Support in Oakville ¦ Cleo Rukovo, NP | Nurse-practitioner-led weight loss support in Oakville. What the programme involves and who it suits. | Weight loss support in Oakville | Service + FAQPage | Home | Contact | Month 4 pre-launch, month 6 full | Not started
/blog/ | Index | 1 | - | no data | - | - | Blog ¦ Luxury Beauty by Cleo R. Oakville | Straight answers to the questions asked most in the treatment room, from a nurse practitioner in Oakville. | Questions we get asked | Blog | Home, footer | Every article | Oct 12 - Nov 8 | Not started
ARTICLES - eight scheduled, three in the backlog. See the Blog Pillars tab for why each exists.
URL path | Page type | Depth | Primary keyword | Vol /mo | KD | Pillar | Links to treatment page | Week | Due | Status
/blog/how-much-does-lip-filler-cost-in-oakville/ | Article | 2 | how much is lip filler | 390 | 11 | Cost & Value | /lip-filler/ | W10 | Oct 12 - 18 | Scheduled
/blog/what-anti-wrinkle-treatment-costs-in-ontario/ | Article | 2 | how much does botox cost in ontario | 90 | 4 | Cost & Value | /anti-wrinkle-injections/ | W11 | Oct 19 - 25 | Scheduled
/blog/how-long-does-lip-filler-last/ | Article | 2 | how long does lip filler last | 1000 | 15 | Longevity & Aftercare | /lip-filler/ | W12 | Oct 26 - Nov 1 | Scheduled
/blog/lip-filler-aftercare/ | Article | 2 | lip filler aftercare | 320 | 14 | Longevity & Aftercare | /lip-filler/ | W13 | Nov 2 - 8 | Scheduled
/blog/what-is-dermaplaning/ | Article | 2 | what is dermaplaning | 880 | 23 | Treatment Explainers | /dermaplaning/ | W14 | Nov 9 - 15 | Scheduled
/blog/what-to-expect-first-filler-appointment/ | Article | 2 | does lip filler hurt | 110 | 7 | First-timer, Safety & Candidacy | /lip-filler/ | W16 | Nov 23 - 29 | Scheduled
/blog/electrolysis-vs-laser-hair-removal/ | Article | 2 | electrolysis vs laser hair removal | 480 | 28 | Treatment Explainers | /electrolysis/ | W18 | Dec 7 - 13 | Scheduled
/blog/baby-botox-and-preventative-treatment/ | Article | 2 | baby botox | 480 | 17 | First-timer, Safety & Candidacy | /anti-wrinkle-injections/ | W22 | Jan 4 - 10 | Scheduled
/blog/aftercare-anti-wrinkle-injections/ | Article | 2 | botox aftercare | 1000 | 32 | Longevity & Aftercare | /anti-wrinkle-injections/ | - | Backlog | Backlog
/blog/what-are-skin-boosters/ | Article | 2 | what are skin boosters | 90 | 23 | Treatment Explainers | /skin-boosters/ | - | Backlog | Backlog
/blog/who-is-not-a-candidate/ | Article | 2 | can you get lip filler while pregnant | 110 | 10 | First-timer, Safety & Candidacy | /lip-filler/ | - | Backlog | Backlog

## Blog Pillars
Blog pillars
What the blog is for, which searches each pillar answers, and which of the eight scheduled articles belongs where. Volumes are Semrush CA, 21 Aug 2026.
FIRST, WHAT WE FOUND
There is no blog yet. Eight articles are scheduled in the tracker at weeks 10, 11, 12, 13, 14, 16, 18 and 22, but none has a topic, a keyword or a title - they are placeholder slots. This tab fills them in.
The five pillars that already exist (Education, Engagement, Trust & Proof, Personality & BTS, Promo & CTA) are INSTAGRAM ENGAGEMENT PILLARS, not search pillars. They organise posts by purpose, not by what anyone types into Google. Across all 102 briefs in content/, not one targets a search term. That is not a criticism of the calendar - it is doing a different job - but it does mean the blog cannot simply inherit them.
The 102 existing briefs are still the best raw material available: they are already written in Cleo's voice and already compliance-checked. The mapping below shows which Instagram pillar feeds which search pillar, so the blog is a rewrite job rather than a research job.
HOW THE INSTAGRAM PILLARS MAP ONTO SEARCH
Instagram pillar | What it does today | Feeds which blog pillar | What that means in practice
Education | Explains a treatment or corrects a myth | Treatment Explainers + First-timer, Safety & Candidacy | The strongest overlap. A myth-busting carousel is an article's outline with the paragraphs removed.
Engagement | Polls, questions, 'this or that' | None directly | Engagement bait has no search demand behind it. Keep it on Instagram - but the questions people answer are free keyword research. Log the recurring ones.
Trust & Proof | Before-and-afters, reviews, credentials | Cost & Value + the /results/ gallery | Feeds the gallery page and the cost articles, where proof does the persuading.
Personality & BTS | Cleo on camera, the room, the day | None directly | No search demand, real conversion value. Belongs on the about page, not the blog.
Promo & CTA | Offers, availability, booking prompts | Cost & Value | Careful here - CNO advertising standards limit discount framing. See the compliance column.
THE FOUR SEARCH PILLARS
Ranked by what to write first. Cost & Value ships first: lowest difficulty, highest intent, and nobody local is answering it.
Pillar | Why it ranks here | Anchor keywords (volume / difficulty) | Total vol /mo | Why this pillar exists | Links to | Compliance note - read before drafting
1. Cost & Value | SHIP FIRST | how much is lip filler (390/KD 11); how much does lip filler cost (260/KD 15); how much is lip filler in canada (110/KD 5); how much does botox cost in ontario (90/KD 4); botox cost canada (90/KD 11) | 940 | Lowest difficulty in the set and the highest commercial intent - somebody pricing a treatment is close to booking. Nobody local answers these honestly, which is exactly why it works. | /lip-filler/, /anti-wrinkle-injections/ | HIGHEST RISK. Never put a price beside a brand name and a benefit claim - that is the Health Canada line. Quote ranges for the treatment category, not the product. No 'best value', no guarantees (CNO).
2. Longevity & Aftercare | Highest volume | how long does lip filler last (1000/KD 15); botox aftercare (1000/KD 32); lip filler aftercare (320/KD 14); lip filler swelling (140/KD 28); what not to do after lip filler (70/KD 18); how long does lip filler swelling last (70/KD 0) | 2600 | The biggest pillar by volume. Reaches people who already have treatment booked or done - which is retention, review requests and word of mouth, not just traffic. | /lip-filler/, /anti-wrinkle-injections/, /dermaplaning/ | Aftercare instruction is clinical guidance. Keep it general and route anything specific to a consult. Never imply a guaranteed duration.
3. First-timer, Safety & Candidacy | Best fit with what already exists | baby botox (480/KD 17); preventative botox (210/KD 45); does lip filler hurt (110/KD 7); can you get lip filler while pregnant (110/KD 10); how to know if lip filler has gone wrong (90/KD 21) | 1000 | Maps almost one-to-one onto the myth-busting and candidacy carousels already written in content/. The 102 briefs in that folder are the raw material - this pillar is mostly rewriting, not researching. | /lip-filler/, /anti-wrinkle-injections/, /about-np-cleo/ | Candidacy and safety content is where a nurse practitioner's credential is the whole advantage. State who is NOT a candidate - it is honest, it ranks, and it filters bad bookings.
4. Treatment Explainers | Widest reach, weakest intent | what is dermaplaning (880/KD 23); what is a dermaplane (880/KD 24); electrolysis vs laser hair removal (480/KD 28); how to dermaplane (210/KD 27); is dermaplaning good for skin (210/KD 35); what is electrolysis hair removal (170/KD 43); what are skin boosters (90/KD 23) | 2920 | Feeds the two lowest-competition treatment pages, dermaplaning and electrolysis, where a page can rank with very little authority behind it. Intent is informational, so judge it on assisted bookings, not direct ones. | /dermaplaning/, /electrolysis/, /skin-boosters/ | Comparison content (electrolysis vs laser) must not claim superiority over another provider's service - that is a CNO advertising breach. Compare the modalities, never the clinics.
THE ARTICLES, ASSIGNED
Eight scheduled slots filled, plus three of the five backlog articles the Site Build tab reserves for Nov 9 - Feb 14. The last two stay open deliberately - fill them from real consult questions.
Week | Due | Article | Pillar | Primary keyword | Vol /mo | KD | Links to treatment page | Status
W10 | Oct 12 - 18 | /blog/how-much-does-lip-filler-cost-in-oakville/ | Cost & Value | how much is lip filler | 390 | 11 | /lip-filler/ | Scheduled
W11 | Oct 19 - 25 | /blog/what-anti-wrinkle-treatment-costs-in-ontario/ | Cost & Value | how much does botox cost in ontario | 90 | 4 | /anti-wrinkle-injections/ | Scheduled
W12 | Oct 26 - Nov 1 | /blog/how-long-does-lip-filler-last/ | Longevity & Aftercare | how long does lip filler last | 1000 | 15 | /lip-filler/ | Scheduled
W13 | Nov 2 - 8 | /blog/lip-filler-aftercare/ | Longevity & Aftercare | lip filler aftercare | 320 | 14 | /lip-filler/ | Scheduled
W14 | Nov 9 - 15 | /blog/what-is-dermaplaning/ | Treatment Explainers | what is dermaplaning | 880 | 23 | /dermaplaning/ | Scheduled
W16 | Nov 23 - 29 | /blog/what-to-expect-first-filler-appointment/ | First-timer, Safety & Candidacy | does lip filler hurt | 110 | 7 | /lip-filler/ | Scheduled
W18 | Dec 7 - 13 | /blog/electrolysis-vs-laser-hair-removal/ | Treatment Explainers | electrolysis vs laser hair removal | 480 | 28 | /electrolysis/ | Scheduled
W22 | Jan 4 - 10 | /blog/baby-botox-and-preventative-treatment/ | First-timer, Safety & Candidacy | baby botox | 480 | 17 | /anti-wrinkle-injections/ | Scheduled
- | Backlog | /blog/aftercare-anti-wrinkle-injections/ | Longevity & Aftercare | botox aftercare | 1000 | 32 | /anti-wrinkle-injections/ | Backlog
- | Backlog | /blog/what-are-skin-boosters/ | Treatment Explainers | what are skin boosters | 90 | 23 | /skin-boosters/ | Backlog
- | Backlog | /blog/who-is-not-a-candidate/ | First-timer, Safety & Candidacy | can you get lip filler while pregnant | 110 | 10 | /lip-filler/ | Backlog
- | Backlog | Open slot - fill from consult questions | Whichever fits |  |  |  |  | Backlog
- | Backlog | Open slot - fill from consult questions | Whichever fits |  |  |  |  | Backlog
THE TWO COMPLIANCE RULES, IN FULL
Health Canada, prescription drug advertising: a prescription product's brand name may not be paired with a benefit claim in advertising to the public. In practice - name the treatment category, describe the outcome; or name the brand and say nothing about what it does. Never both in the same breath.
CNO advertising standards: no guarantees of outcome, no claims of superiority over another provider, no testimonials that imply a guaranteed result. This binds Cleo personally as a registered nurse practitioner, not just the business.

## Reviews
Review tracker
Baseline 12 reviews at 5.0. Target 18 to 22 new ones across the six months, roughly one every ten days. Ask inside 24 hours or the number does not move. |  |  |  |  | Asks sent |  | Reviews landed
Date asked | Patient (initials) | How we asked | Asked by | Review received | Date received | Platform | Replied | Notes

## Citations
Citations and NAP
One name, one address, one phone number, everywhere. The postal code is L6M 4L9 — it is wrong on most of these today.
Directory | Listing URL | Claimed | Name correct | Address and postal code correct | Phone correct | Website URL current | Status | Date done | Notes
Google Business Profile | https://share.google/FpK3RhUmP2n3dVgUQ | Yes |  |  |  |  | Not started
Birdeye | [6 empty] | Not started
Facebook | [6 empty] | Not started
Fresha | https://www.fresha.com/lvp/luxury-beauty-by-cleo-r-preserve-drive-oakville-X417M2 | [5 empty] | Not started
Yelp.ca | [6 empty] | Not started
Yellow Pages | [6 empty] | Not started
Apple Maps | [6 empty] | Not started
Bing Places | [6 empty] | Not started
RateMDs | [6 empty] | Not started
Canadian chamber directories | [6 empty] | Not started
Oakville Chamber of Commerce | [6 empty] | Not started
411.ca | [6 empty] | Not started
Cylex Canada | [6 empty] | Not started
Foursquare | [6 empty] | Not started
Instagram profile | [6 empty] | Not started
Booking system profile | [6 empty] | Not started
Halton business directory | [6 empty] | Not started
bookbeauty.ca | https://bookbeauty.ca/listing/luxury-beauty-by-cleo-r/
fresha.com

## Local Citations
Local citations — the build list
The Citations tab fixes listings that already exist. This one builds listings where there are none. Decide the record once, then paste it, unchanged, into every form below. |  |  |  |  | Submitted |  | Still to do
THE RECORD — paste this, exactly, every time
Field | Value |  |  | Where it gets decided
Business name (exact) | Luxury Beauty by Cleo R. |  |  | Use this spelling everywhere. No 'Med Spa', no 'Inc', no variations
Practitioner | Cleo Rukovo, NP |  |  | Nurse practitioner. Some healthcare directories list the person, not the practice
Address line 1 | 3060 Preserve Drive |  |  | Confirmed
Suite / unit |  |  |  | Waiting on the Allure conversation. This is what separates you from their listing
City | Oakville |  |  | Confirmed
Province | Ontario |  |  | Write 'Ontario' in full, or 'ON' — pick one and never mix them
Postal code | L6M 4L9 |  |  | Confirmed by Cleo, 21 Aug 2026. Listings showing L6M 0T9 are the error - verify against Canada Post before the mass correction
Country | Canada |  |  | Confirmed
Phone | (416) 294-0452 |  |  | One number, everywhere. A local 905 or 289 line beats the 416 mobile if you can get one
Email | Luxury.beautyaestheticz@gmail.com |  |  | One address. Currently split between crukovo@ and luxury.beautyaestheticz@
Website | https://luxurybeautybycleo.ca |  |  | Use the booking link until the site is live in October, then switch every listing
Booking URL | IG only |  |  | Needed before any directory that offers a booking button
Primary category | Medical Spa |  |  | Set on the Google profile first, then match it everywhere else
Secondary categories | Skin care clinic Weight loss service |  |  | Chosen to avoid colliding with Allure's listing
Short description (under 250 characters) |  |  |  | Names the town and the treatments. No prescription drug names, no benefit claims
Long description | Luxury Beauty by Cleo R. is a nurse practitioner-led medical spa in Oakville, Ontario, serving clients across Burlington, Mississauga, Milton and Halton Region. Our services include lip filler, dermal filler for volume loss, anti-wrinkle injections, jawline slimming, skin boosters for hydration and glow, dermaplaning, and electrolysis. Every visit begins with a one-on-one consultation so we can plan the right approach for your features and your goals. Our philosophy is simple: the right product, the right technique, and never more than you need. Every treatment is performed by Cleo Rukovo, NP. Book your consultation today. |  |  | Same rules. Write once, reuse everywhere
Hours — Monday | Closed |  |  | All seven days. 'Closed' is an answer; blank is not
Hours — Tuesday | Closed
Hours — Wednesday | Closed
Hours — Thursday | Closed
Hours — Friday | 10:00 AM–8:00 PM
Hours — Saturday | Closed
Hours — Sunday | Closed |  |  | The only hours on record anywhere today are Sunday 12 to 5
Year established | 2023
Service area | Oakville, Burlington, Milton, Mississauga, Glen Abbey, Joshua Creek, Bronte |  |  | Used where a directory asks for a service radius
Logo file | added |  |  | From design/brand
Cover photo | added
Amber means still undecided. Every amber row above has a matching row on the Waiting On Cleo tab. Do not submit to anything below until they are all filled in — a wrong detail submitted 28 times is 28 corrections later.
SUBMISSION QUEUE — one a day in the citation slot, once the record is settled
Directory | Type | Priority | Where to start | Account needed | Verified live | Status | Date submitted | Live listing URL | NAP checked | Notes
Oakville News business listing | Local | Medium | oakvillenews.org |  |  | In progress
Nextdoor business page, Oakville | Local | Medium | business.nextdoor.com |  |  | Done |  | https://ca.nextdoor.com/page/luxury-beauty-by-cleo-r-oakville-on
Nurse Practitioners' Association of Ontario | Healthcare | High | npao.org |  |  | Not applicable
Doctify Canada | Healthcare | Medium | doctify.com |  |  | Not applicable
Booksy | Healthcare | Medium | booksy.com |  |  | In progress |  |  |  | free trial need phone verifcation
Vagaro | Healthcare | Medium | vagaro.com |  |  | In progress |  |  |  | need payment
Spas of America | Healthcare | Low | spasofamerica.com |  |  | Not applicable
Canpages | Canadian | Medium | canpages.ca |  |  | Blocked
ProfileCanada | Canadian | Medium | profilecanada.com |  |  | Not started
n49 | Canadian | Medium | n49.com |  |  | Not started
Hotfrog Canada | Canadian | Low | hotfrog.ca |  |  | Not started
Yably Canada | Canadian | Low | yably.ca |  |  | Not started
Waze business listing | Maps | Medium | waze.com |  |  | Not started
Here WeGo | Maps | Low | here.com |  |  | Not started
LinkedIn company page | Social | Medium | linkedin.com |  |  | Not started
Pinterest business profile | Social | Low | pinterest.com |  |  | Not started
TikTok business profile | Social | Medium | tiktok.com |  |  | Not started
Domains in 'Where to start' are a starting point, not gospel. Canadian directories close and change hands. The first pass on every row is confirming it still exists and still takes a free listing — if it does not, set Status to Not applicable and say so in Notes rather than leaving it silent.
Google, Yelp.ca, Facebook, Fresha, Yellow Pages, Apple Maps, Bing Places, RateMDs, 411.ca, Cylex, Foursquare and the chamber listings are not repeated here — they already exist and live on the Citations tab.
Every listing built before the site launches carries the booking link. In launch week, week of 5 October, every one of them gets updated to the live site URL. That is a task on the Tasks tab, not a thing to remember.

## Heatmap Tracking
Heatmap tracking
Microsoft Clarity - free, unlimited sessions. Rankings tell you who arrived; this tells you what they did next. A page that ranks and does not book looks like a win without it.
A note on Semrush: it has no heatmap product. Semrush measures the search results page and the competition; a heatmap needs a tag on your own site recording real visitors. They are different instruments and you need both.
1. SETUP - all of it before the site goes live
Step | Owner | When | Notes | Status
Create the Microsoft Clarity account and project for luxurybeautybycleo.ca | Agency | Before launch | Free, no session cap, no credit card. clarity.microsoft.com | Not started
Install the Clarity tag sitewide, in the head of every page | Agency | Before launch | Must be live ON launch day. Behaviour from the first weeks cannot be recovered later | Not started
Verify it is recording - open the site, then check the session appears | Agency | Before launch |  | Not started
Link Clarity to Google Analytics | Agency | Launch week | Lets you jump from a traffic number straight to the recordings behind it | Not started
Set the booking-link click as a tracked event | Agency | Launch week | Without it you see where people click, not whether they booked | Not started
Set up a mobile-only filter and save it | Agency | Launch week | Most of this audience is on a phone. Desktop-weighted heatmaps will point you the wrong way | Not started
Add the weekly heatmap review to the Monday insights block | Agency | Launch week | Daily Routine tab, Monday slot. A tool nobody opens is worth nothing | Not started
2. WHAT WE REVIEW, AND HOW OFTEN
Page | Heatmap type | The question it answers | Cadence | What to do about it
/ | Scroll + click | Do visitors get past the hero to the treatments? | Weekly for month 1, then monthly | If most sessions stop before the treatment list, the hero is too tall or says too little.
/lip-filler/ | Scroll + click | Do they reach the booking CTA at all? | Weekly for month 1, then monthly | The highest-volume treatment page at KD 7. If scroll depth to the CTA is under 50 per cent, move the CTA up.
/anti-wrinkle-injections/ | Scroll + click | Same, on the biggest local term (480/mo) | Weekly for month 1, then monthly | Watch for people bouncing at the compliance wording - it reads as evasive if handled badly.
/dermal-filler-facial-balancing/ | Scroll | Is the page too long before the price or CTA? | Monthly
/contact/ | Click | Are they clicking something that is not a link? | Weekly for month 1, then monthly | Dead clicks on the address or phone number mean people expect tap-to-call or tap-for-directions. Cheap fix, real bookings.
/results/ | Scroll + click | Do they click a photo expecting it to enlarge? | Monthly | Dead clicks on gallery images are the commonest finding on a clinic site.
/blog/ articles | Scroll | Do readers reach the link to the treatment page? | Monthly | An article read to 40 per cent that never surfaces the treatment link is traffic doing nothing.
Mobile, every page | Scroll + click | Is the booking button reachable with one thumb? | Weekly for month 1, then monthly | Filter Clarity to mobile only. Most of this audience is on a phone - desktop findings will mislead you.
3. FINDINGS LOG - the tab that turns watching into changing
A finding with no change logged beside it is not a finding, it is a note. Fill the right-hand columns or do not bother with the left-hand ones.
Date | Page | What we saw | Evidence (recording or heatmap link) | Change made | Date changed | Status | Did it work?
4. WHAT GOOD LOOKS LIKE
What we measure | The threshold | What it means when it is missed
Visitors scrolling to the booking CTA | 50 per cent or better | Under 50, the CTA is too far down or the copy above it is not earning the scroll
Rage clicks on a treatment page | Zero | A rage click is a visitor clicking the same spot repeatedly. It always means something looks clickable and is not
Dead clicks | Under 2 per cent of sessions | Usually images, phone numbers or addresses that are not linked
Quick-back sessions | Under 25 per cent | Landing and leaving within seconds. On a treatment page it usually means the title tag promised something the page did not
Sessions reviewed by hand | 10 a week for month 1, then 10 a month | Recordings tell you why the heatmap looks the way it does. The heatmap alone only tells you what

## Metrics
Monthly numbers
Fill at the end of each month. Compare against the baseline column, not against last month.
What we track | Baseline (17 Aug) | Target by 14 Feb | End Sep | End Oct | End Nov | End Dec | End Jan | Mid Feb | Notes
Google reviews | 12 | 30 to 34, still at or near 5.0
Google review average | 5.0 | At or near 5.0
Calls from Google profile | 0 | Up on baseline every month
Direction requests from Google | 19 | Up on baseline every month
Google profile views | 205 | Up on baseline every month
GBP posts published in the month | 3 | 20 or more, every month
Map pack position: nurse injector oakville |  | Visible in the pack | [6 empty] | No measurable search volume in Semrush. Keep tracking it - it is free to own - but judge the month on botox oakville and lip filler oakville
Map pack position: botox oakville |  | Visible in the pack
Map pack position: lip filler oakville |  | Visible in the pack
Instagram profile visits | 587 | Up on baseline
Instagram link taps | 2 | Rising faster than profile visits
Reels published in the month | 1 | Four, one a week
DMs received | Not tracked | Tracked weekly from week 1
Consultations booked | Not tracked | Tracked weekly, attributed to source
Ad spend | Not supplied | Confirmed and split 70/20/10
Cost per DM from ads |  | Falling month on month
Website sessions | No site | From launch in October, rising month on month
Search Console impressions | No site | Rising month on month from October
Pages indexed | No site | Every page, confirmed in Search Console
Daily slot completion rate |  | 85 per cent or better
Semrush visibility (%) |  | Rising every month once tracking is live | [6 empty] | Position Tracking. Needs the Semrush project created first - task 159
Semrush Site Audit health score |  | 90 or better within a month of launch | [6 empty] | Site Audit cannot run until the site resolves
Organic keywords ranking (Semrush) | 0 | 60 or more by 14 Feb | [6 empty] | Baseline is genuinely zero - the domain returns no rows in the Semrush CA database today
Map pack position: med spa oakville |  | Visible in the pack | [6 empty] | 140 searches a month, KD 29
Clarity sessions recorded |  | Every session from launch onward | [6 empty] | Microsoft Clarity, free tier, no session cap
Visitors scrolling to the booking CTA (%) |  | 50 per cent or better | [6 empty] | Clarity scroll heatmap on the treatment pages
Rage clicks per 100 sessions |  | Zero on the treatment pages | [6 empty] | Clarity. Any rage click is a broken expectation

## Waiting On Cleo
Waiting on Cleo
Access, assets and answers. Most delay in work like this comes from waiting on these. The top four are what the build waits on.
Type | What we need | Needed by | Why it blocks us | Status | Date received | Notes
Access | Google Business Profile, and which email holds it | 2026-08-21 | Nothing on the profile can start until this is settled | Not started
Answer | Real opening hours for every day | 2026-08-21 | The hours on Google are wrong until we have these | Not started
Asset | Treatment list with current pricing | 2026-08-26 | Sitemap, service pages and the GBP services list all key off it | Not started
Access | Domain registrar login for luxurybeautybycleo.ca | 2026-08-28 | DNS has to be pointed before the build can start on 1 September | Not started
Answer | DESIGN SIGN-OFF on the wireframes and the look | 2026-08-31 | The build gate. Everything after it slips one-for-one | Not started
Asset | Photos of the treatment room and the space | 2026-08-28 | GBP photos and every website page | Not started
Asset | A current headshot | 2026-08-28 | GBP, Instagram and the site | Not started
Asset | Logo files and any brand assets you already have | 2026-08-28 | The design cannot be finalised without them | Not started
Asset | Signed before-and-after consent form | 2026-09-06 | Determines what we are allowed to publish anywhere | Not started
Access | Meta Business account and ad account | 2026-09-20 | Needed to build audiences and run ads | Not started
Access | Instagram collaborator invitation | 2026-08-28 | Needed to fix the name field, bio and link | Not started
Access | Booking system login | 2026-09-06 | Needed for the booking link and the lookalike audience | Not started
Answer | Whether Allure allows your own signage and suite designation | 2026-08-23 | Decides how we build the Google listing | Not started
Answer | The three competitors you want to be measured against | 2026-08-23 | Shapes what we track and benchmark | Not started
Answer | Your ideal patient, in your own words | 2026-09-13 | Ad audiences and page copy | Not started
Answer | Current monthly spend on Instagram and Google ads | 2026-09-13 | Cannot recommend a budget without it | Not started
Answer | Approval of the home page copy | 2026-09-13 | Home and contact cannot go into staging without it | Not started
Answer | Approval of the treatment page copy | 2026-09-27 | Every claim has to be one you can stand behind | Not started
Answer | The questions you get asked most in consults | 2026-10-18 | The articles are written from them, not invented | Not started
Answer | Commitment to the daily routine | 2026-08-21 | Five slots a day. Without them the rest of the plan does not compound | Not started