## Start Here
Getting Found in Oakville — six-month tracker
Working file for Luxury Beauty by Cleo R. Companion to seo-roadmap-6-month.docx
THE SHAPE OF IT
Runs | Monday 17 August 2026 to Sunday 14 February 2027. Twenty-six weeks, six months.
Right now | The rest of August is Google Business Profile and citations. Nothing else.
Week of Aug 24 | Website planning and design. Sitemap, wireframes, keyword-to-page map, copy outline.
Aug 31 | Design sign-off. This is the date the build waits on.
Sept 1 | Build starts. Launch target is the week of 5 October.
HOW THIS WORKS
Every day | Open the Daily Log. Six slots, five of them daily, the reel on Wednesday. Mark each one.
The routine | The Daily Routine tab says what each slot actually means. Read it once, then work off the log.
The projects | The Tasks tab holds the one-off work. Filter Status to 'In progress' and 'Not started'.
You edit | Status, Date done, and Notes. Leave the rest unless the plan genuinely changes.
Blocked? | Set Status to Blocked and write what you are waiting on in Notes. Blocked rows turn red.
Weekly | Monday: profile insights. Wednesday: batch the content and film the reel. Friday: log the week.
Monthly | Fill the Metrics tab. Compare against the baseline column, not against last month.
THE TWO THINGS THAT DECIDE THIS
Reviews | Twelve today. The ask goes out inside 24 hours of every appointment or the number does not move.
The daily log | Five slots a day is not a lot. Missing them for a fortnight undoes a month of the rest.
WHERE THINGS STAND
Project tasks
Not started
In progress
Blocked
Done
Overdue and not done
Percent complete
Daily slots done
Daily slots missed
Daily completion rate
Import to Google Sheets: drive.google.com > New > File upload > pick this file > open with Google Sheets.

## Daily Routine
The daily routine
Six slots. Five of them every weekday, the reel on Wednesday. This is the tab that explains the work; the Daily Log is the tab you tick.
Slot | Task | Cadence | What it involves | Owner | Logged on | Status
EVERY DAY
1 | Google Business Profile post | Every weekday | One post a day. Rotate the five types across the week: treatment spotlight, FAQ or myth, before and after, offer or availability, practice update. Copy and images come from the content calendar. Every post ends with the booking link. | Cleo | GBP Posts tab | Not started
2 | Instagram post or stories | Every weekday | A feed post on the calendar days, two or three stories on the rest. Location-tag Oakville every time, write the alt text every time, use the local hashtag set. | Cleo | Content calendar | Not started
3 | Reel | Once a week — Wednesday | One reel a week, filmed and cut in the Wednesday batch block. Rotate the four types across the month: a treatment in fifteen seconds, a myth-buster, behind the scenes in the room, a patient question answered to camera. Reuse each cut as a story and a GBP video. | Cleo | Daily Log tab | Not started
4 | On-page optimisation | Every weekday | Before launch: keyword-to-page mapping, drafting title tags and meta descriptions, writing page copy for the build. After launch: one page improved a day on rotation — title tag, H1, internal links, image alt text, schema, thin content topped up. | Agency | Tasks tab | Not started
5 | Review ask | Every weekday | The WhatsApp message inside 24 hours to every patient seen that day, and a reply to any review that landed. This is the single highest-return thing in the plan. | Cleo | Reviews tab | Not started
6 | Citations | Daily to week 4, then weekly | One directory a day claimed or corrected until the list is clean, then one a week to keep it clean. Name, address and phone identical everywhere, no exceptions. | Agency | Citations tab | Not started
EVERY WEEK
Mon | Google profile insights and rank check | Weekly | Calls, views and direction requests for the week. Where the map pack has you for the three target terms. Two minutes, written down, every Monday. | Agency | Metrics tab | Not started
Wed | Content and reel batch | Weekly | Film the reel, batch the week's GBP posts and Instagram captions so the daily slots are a five-minute publish rather than a blank page. | Both | Content calendar | Not started
Fri | Log the week | Weekly | Fill in the week's numbers, close out the Tasks tab, flag anything blocked. Ad review every second Friday. | Agency | Tasks tab | Not started
EVERY MONTH
| Fill the Metrics tab | Monthly | Every number for the month end. Compare against the baseline column, not against last month. | Agency | Metrics tab | Not started
| Refresh the Google profile | Monthly | Services list, questions and answers, photo set. A profile that never changes stops earning. | Agency | Tasks tab | Not started
| Competitor and query check | Monthly | What the three named competitors are doing, and which queries Search Console shows you sitting just outside the first page for. | Agency | Metrics tab | Not started
| Review the month's best work | Monthly | The posts that drove profile visits and the pages that drove sessions. More of those next month. | Both | Metrics tab | Not started
The reel is once a week, on Wednesday, filmed in the Wednesday batch block. Do not try to do one a day.
Before the site is live, the on-page slot is preparation: keyword mapping, title tags, meta descriptions, page copy.
From launch onward it is one real page improved a day, on rotation, so no page goes six months untouched.
Compliance applies to Google posts exactly as it applies to Instagram. Nothing names a prescription drug.

## Daily Log
Daily log
One row per weekday, 17 August 2026 to 12 February 2027. Mark each slot Done, Missed or N/A. The reel column is only live on Wednesdays. |  |  |  |  | Slots done |  | Slots missed |  | Completion
|  |  | GBP posts |  | Reels |  | Review asks |  | Days logged
Date | Day | Week | GBP post | IG post / story | Reel | On-page | Review ask | Citation | Done | Notes
AUGUST 2026
2026-08-17 | Mon | W1 |  |  | N/A
2026-08-18 | Tue | W1 |  |  | N/A
2026-08-19 | Wed | W1
2026-08-20 | Thu | W1 |  |  | N/A
2026-08-21 | Fri | W1 |  |  | N/A
2026-08-24 | Mon | W2 |  |  | N/A
2026-08-25 | Tue | W2 |  |  | N/A
2026-08-26 | Wed | W2
2026-08-27 | Thu | W2 |  |  | N/A
2026-08-28 | Fri | W2 |  |  | N/A
2026-08-31 | Mon | W3 |  |  | N/A
SEPTEMBER 2026
2026-09-01 | Tue | W3 |  |  | N/A
2026-09-02 | Wed | W3
2026-09-03 | Thu | W3 |  |  | N/A
2026-09-04 | Fri | W3 |  |  | N/A
2026-09-07 | Mon | W4 |  |  | N/A
2026-09-08 | Tue | W4 |  |  | N/A
2026-09-09 | Wed | W4
2026-09-10 | Thu | W4 |  |  | N/A
2026-09-11 | Fri | W4 |  |  | N/A
2026-09-14 | Mon | W5 |  |  | N/A
2026-09-15 | Tue | W5 |  |  | N/A
2026-09-16 | Wed | W5
2026-09-17 | Thu | W5 |  |  | N/A
2026-09-18 | Fri | W5 |  |  | N/A
2026-09-21 | Mon | W6 |  |  | N/A
2026-09-22 | Tue | W6 |  |  | N/A
2026-09-23 | Wed | W6
2026-09-24 | Thu | W6 |  |  | N/A
2026-09-25 | Fri | W6 |  |  | N/A
2026-09-28 | Mon | W7 |  |  | N/A
2026-09-29 | Tue | W7 |  |  | N/A
2026-09-30 | Wed | W7
OCTOBER 2026
2026-10-01 | Thu | W7 |  |  | N/A
2026-10-02 | Fri | W7 |  |  | N/A
2026-10-05 | Mon | W8 |  |  | N/A
2026-10-06 | Tue | W8 |  |  | N/A
2026-10-07 | Wed | W8
2026-10-08 | Thu | W8 |  |  | N/A
2026-10-09 | Fri | W8 |  |  | N/A
2026-10-12 | Mon | W9 |  |  | N/A
2026-10-13 | Tue | W9 |  |  | N/A
2026-10-14 | Wed | W9
2026-10-15 | Thu | W9 |  |  | N/A
2026-10-16 | Fri | W9 |  |  | N/A
2026-10-19 | Mon | W10 |  |  | N/A
2026-10-20 | Tue | W10 |  |  | N/A
2026-10-21 | Wed | W10
2026-10-22 | Thu | W10 |  |  | N/A
2026-10-23 | Fri | W10 |  |  | N/A
2026-10-26 | Mon | W11 |  |  | N/A
2026-10-27 | Tue | W11 |  |  | N/A
2026-10-28 | Wed | W11
2026-10-29 | Thu | W11 |  |  | N/A
2026-10-30 | Fri | W11 |  |  | N/A
NOVEMBER 2026
2026-11-02 | Mon | W12 |  |  | N/A
2026-11-03 | Tue | W12 |  |  | N/A
2026-11-04 | Wed | W12
2026-11-05 | Thu | W12 |  |  | N/A
2026-11-06 | Fri | W12 |  |  | N/A
2026-11-09 | Mon | W13 |  |  | N/A
2026-11-10 | Tue | W13 |  |  | N/A
2026-11-11 | Wed | W13
2026-11-12 | Thu | W13 |  |  | N/A
2026-11-13 | Fri | W13 |  |  | N/A
2026-11-16 | Mon | W14 |  |  | N/A
2026-11-17 | Tue | W14 |  |  | N/A
2026-11-18 | Wed | W14
2026-11-19 | Thu | W14 |  |  | N/A
2026-11-20 | Fri | W14 |  |  | N/A
2026-11-23 | Mon | W15 |  |  | N/A
2026-11-24 | Tue | W15 |  |  | N/A
2026-11-25 | Wed | W15
2026-11-26 | Thu | W15 |  |  | N/A
2026-11-27 | Fri | W15 |  |  | N/A
2026-11-30 | Mon | W16 |  |  | N/A
DECEMBER 2026
2026-12-01 | Tue | W16 |  |  | N/A
2026-12-02 | Wed | W16
2026-12-03 | Thu | W16 |  |  | N/A
2026-12-04 | Fri | W16 |  |  | N/A
2026-12-07 | Mon | W17 |  |  | N/A
2026-12-08 | Tue | W17 |  |  | N/A
2026-12-09 | Wed | W17
2026-12-10 | Thu | W17 |  |  | N/A
2026-12-11 | Fri | W17 |  |  | N/A
2026-12-14 | Mon | W18 |  |  | N/A
2026-12-15 | Tue | W18 |  |  | N/A
2026-12-16 | Wed | W18
2026-12-17 | Thu | W18 |  |  | N/A
2026-12-18 | Fri | W18 |  |  | N/A
2026-12-21 | Mon | W19 |  |  | N/A
2026-12-22 | Tue | W19 |  |  | N/A
2026-12-23 | Wed | W19
2026-12-24 | Thu | W19 |  |  | N/A
2026-12-25 | Fri | W19 |  |  | N/A
2026-12-28 | Mon | W20 |  |  | N/A
2026-12-29 | Tue | W20 |  |  | N/A
2026-12-30 | Wed | W20
2026-12-31 | Thu | W20 |  |  | N/A
JANUARY 2027
2027-01-01 | Fri | W20 |  |  | N/A
2027-01-04 | Mon | W21 |  |  | N/A
2027-01-05 | Tue | W21 |  |  | N/A
2027-01-06 | Wed | W21
2027-01-07 | Thu | W21 |  |  | N/A
2027-01-08 | Fri | W21 |  |  | N/A
2027-01-11 | Mon | W22 |  |  | N/A
2027-01-12 | Tue | W22 |  |  | N/A
2027-01-13 | Wed | W22
2027-01-14 | Thu | W22 |  |  | N/A
2027-01-15 | Fri | W22 |  |  | N/A
2027-01-18 | Mon | W23 |  |  | N/A
2027-01-19 | Tue | W23 |  |  | N/A
2027-01-20 | Wed | W23
2027-01-21 | Thu | W23 |  |  | N/A
2027-01-22 | Fri | W23 |  |  | N/A
2027-01-25 | Mon | W24 |  |  | N/A
2027-01-26 | Tue | W24 |  |  | N/A
2027-01-27 | Wed | W24
2027-01-28 | Thu | W24 |  |  | N/A
2027-01-29 | Fri | W24 |  |  | N/A
FEBRUARY 2027
2027-02-01 | Mon | W25 |  |  | N/A
2027-02-02 | Tue | W25 |  |  | N/A
2027-02-03 | Wed | W25
2027-02-04 | Thu | W25 |  |  | N/A
2027-02-05 | Fri | W25 |  |  | N/A
2027-02-08 | Mon | W26 |  |  | N/A
2027-02-09 | Tue | W26 |  |  | N/A
2027-02-10 | Wed | W26
2027-02-11 | Thu | W26 |  |  | N/A
2027-02-12 | Fri | W26 |  |  | N/A

## Tasks
ID | Month | Week | Due | Area | Task | Owner | Cadence | Priority | Status | Date done | Notes / blockers
1 | Month 1 | W1 | 2026-08-23 | Google profile | Find out who owns the Google Business Profile and which email holds it | Cleo | One-off | High | Not started
2 | Month 1 | W1 | 2026-08-23 | Google profile | Confirm with Allure whether you can use your own signage and suite designation | Cleo | One-off | High | Not started
3 | Month 1 | W1 | 2026-08-23 | Google profile | Claim and verify the Google Business Profile | Agency | One-off | High | Not started
4 | Month 1 | W1 | 2026-08-23 | Google profile | Correct the GBP address to L6M 0T9 and add the suite designation | Agency | One-off | High | Not started
5 | Month 1 | W1 | 2026-08-23 | Google profile | Set real opening hours on GBP for every day of the week | Agency | One-off | High | Not started
6 | Month 1 | W1 | 2026-08-23 | Google profile | Choose the primary GBP category | Agency | One-off | High | Not started
7 | Month 1 | W1 | 2026-08-23 | Google profile | Choose secondary categories that avoid colliding with Allure's listing | Agency | One-off | High | Not started
8 | Month 1 | W1 | 2026-08-23 | Google profile | Replace the dead website link on GBP with the booking link until the site is live | Agency | One-off | High | Not started
9 | Month 1 | W1 | 2026-08-23 | Google profile | Upload real photos to GBP: treatment room, you, the space | Both | One-off | High | Not started
10 | Month 1 | W1 | 2026-08-23 | Citations | Decide on one email address and one phone number to use everywhere | Cleo | One-off | High | Not started
11 | Month 1 | W1 | 2026-08-23 | Citations | Audit every listing that mentions the practice and record the wrong NAP on the Citations tab | Agency | One-off | High | Not started
12 | Month 1 | W1 | 2026-08-23 | Daily routine | Start the daily routine: GBP post, Instagram, on-page, review ask, citation | Cleo | Daily | High | Not started
13 | Month 1 | W1 | 2026-08-23 | Daily routine | Agree who does which daily slot and put it in the calendar | Both | One-off | High | Not started
14 | Month 1 | W1 | 2026-08-23 | Measurement | Record the baseline: 12 reviews, 5.0 average, GBP calls, views and direction requests | Agency | One-off | High | Not started
15 | Month 1 | W1 | 2026-08-23 | Measurement | Send us your real opening hours for every day of the week | Cleo | One-off | High | Not started
16 | Month 1 | W1 | 2026-08-23 | Measurement | Name the three competitors you want to be measured against | Cleo | One-off | Medium | Not started
17 | Month 1 | W2 | 2026-08-30 | Citations | Correct postal code to L6M 0T9 on Birdeye | Agency | One-off | High | Not started
18 | Month 1 | W2 | 2026-08-30 | Citations | Correct postal code to L6M 0T9 on Facebook | Agency | One-off | High | Not started
19 | Month 1 | W2 | 2026-08-30 | Citations | Correct postal code to L6M 0T9 on Fresha | Agency | One-off | High | Not started
20 | Month 1 | W2 | 2026-08-30 | Citations | Correct postal code to L6M 0T9 on Yelp.ca | Agency | One-off | Medium | Not started
21 | Month 1 | W2 | 2026-08-30 | Citations | Correct postal code to L6M 0T9 on Yellow Pages | Agency | One-off | Medium | Not started
22 | Month 1 | W2 | 2026-08-30 | Website | PLANNING WEEK: agree the sitemap and the full page inventory | Both | One-off | High | Not started
23 | Month 1 | W2 | 2026-08-30 | Website | Build the keyword-to-page map so every page has one job | Agency | One-off | High | Not started
24 | Month 1 | W2 | 2026-08-30 | Website | Wireframe the home page, the contact page and the treatment page template | Agency | One-off | High | Not started
25 | Month 1 | W2 | 2026-08-30 | Website | Pull the brand kit — colours, type, logo — from design/brand | Agency | One-off | Medium | Not started
26 | Month 1 | W2 | 2026-08-30 | Website | Send the domain registrar login for luxurybeautybycleo.ca | Cleo | One-off | High | Not started
27 | Month 1 | W2 | 2026-08-30 | Website | Send the treatment list with current pricing | Cleo | One-off | High | Not started
28 | Month 1 | W2 | 2026-08-30 | Website | DESIGN REVIEW with Cleo. Sign-off due Friday 28 August | Both | One-off | High | Not started
29 | Month 1 | W2 | 2026-08-30 | Instagram | Rewrite the Instagram name field to read 'Cleo ¦ Nurse Injector Oakville' | Agency | One-off | High | Not started
30 | Month 1 | W2 | 2026-08-30 | Instagram | Rewrite the Instagram bio to name the town and the treatments | Agency | One-off | High | Not started
31 | Month 1 | W2 | 2026-08-30 | Instagram | Fix the link in bio so it no longer points at the dead domain | Agency | One-off | High | Not started
32 | Month 1 | W2 | 2026-08-30 | Instagram | Start location-tagging Oakville on every post | Cleo | Ongoing | High | Not started
33 | Month 1 | W2 | 2026-08-30 | Reviews | Write the WhatsApp review-ask message | Agency | One-off | High | Not started
34 | Month 1 | W2 | 2026-08-30 | Reviews | Reply to all 12 existing reviews | Cleo | One-off | Medium | Not started
35 | Month 1 | W3 | 2026-09-06 | Website | DESIGN SIGN-OFF DUE Monday 31 August | Cleo | One-off | High | Not started
36 | Month 1 | W3 | 2026-09-06 | Website | BUILD STARTS 1 SEPTEMBER: hosting sorted, DNS pointed, platform set up | Agency | One-off | High | Not started
37 | Month 1 | W3 | 2026-09-06 | Website | Scaffold the page structure agreed in planning | Agency | One-off | High | Not started
38 | Month 1 | W3 | 2026-09-06 | Website | Write the home page copy and get it approved | Both | One-off | High | Not started
39 | Month 1 | W3 | 2026-09-06 | Website | Write the contact page copy with the corrected NAP and hours | Agency | One-off | High | Not started
40 | Month 1 | W3 | 2026-09-06 | Citations | Correct postal code to L6M 0T9 on Apple Maps | Agency | One-off | Medium | Not started
41 | Month 1 | W3 | 2026-09-06 | Citations | Correct postal code to L6M 0T9 on Bing Places | Agency | One-off | Medium | Not started
42 | Month 1 | W3 | 2026-09-06 | Citations | Correct postal code to L6M 0T9 on RateMDs | Agency | One-off | Low | Not started
43 | Month 1 | W3 | 2026-09-06 | Google profile | Fill out the GBP services list with a plain description of each treatment | Agency | One-off | Medium | Not started
44 | Month 1 | W3 | 2026-09-06 | Google profile | Add a working booking link to GBP | Agency | One-off | High | Not started
45 | Month 1 | W3 | 2026-09-06 | Reviews | Start sending the review ask within 24 hours of every appointment | Cleo | Daily | High | Not started
46 | Month 1 | W3 | 2026-09-06 | Compliance | Confirm the signed before-and-after consent form is on file | Cleo | One-off | High | Not started
47 | Month 1 | W4 | 2026-09-13 | Website | Home and contact pages complete in staging: NAP, hours, booking link, schema | Agency | One-off | High | Not started
48 | Month 1 | W4 | 2026-09-13 | Website | LocalBusiness and Service schema on every page built so far | Agency | One-off | High | Not started
49 | Month 1 | W4 | 2026-09-13 | Website | Title tags and meta descriptions for the home and contact pages | Agency | One-off | High | Not started
50 | Month 1 | W4 | 2026-09-13 | Citations | Correct postal code to L6M 0T9 on the Canadian chamber directories | Agency | One-off | Low | Not started
51 | Month 1 | W4 | 2026-09-13 | Citations | Claim any listing about the practice that is not under your control | Agency | One-off | Medium | Not started
52 | Month 1 | W4 | 2026-09-13 | Citations | Verify every corrected listing now shows identical name, address and phone | Agency | One-off | High | Not started
53 | Month 1 | W4 | 2026-09-13 | Google profile | Seed the GBP questions section with real questions and answers | Both | One-off | Medium | Not started
54 | Month 1 | W4 | 2026-09-13 | Google profile | Post to GBP every weekday from the content calendar | Cleo | Daily | High | Not started
55 | Month 1 | W4 | 2026-09-13 | Compliance | Compliance pass on the 21 briefs naming Botox or Dysport in client-facing copy | Agency | One-off | High | Not started
56 | Month 1 | W4 | 2026-09-13 | Compliance | Compliance rules apply to GBP posts too — brief Cleo on what cannot be named | Agency | One-off | High | Not started
57 | Month 1 | W4 | 2026-09-13 | Measurement | Set up the analytics property ready for launch | Agency | One-off | Medium | Not started
58 | Month 1 | W4 | 2026-09-13 | Ads | Send us your current monthly Instagram and Google ad spend | Cleo | One-off | High | Not started
59 | Month 2 | W5 | 2026-09-20 | Website | Build the treatment pages: lip filler, dermal filler and facial balancing | Agency | One-off | High | Not started
60 | Month 2 | W5 | 2026-09-20 | Website | Write the copy for those pages and confirm every claim is one you can stand behind | Both | One-off | High | Not started
61 | Month 2 | W5 | 2026-09-20 | Website | Title tag, meta description and H1 on every treatment page built | Agency | One-off | High | Not started
62 | Month 2 | W5 | 2026-09-20 | Reviews | Design and print the QR review card for the treatment room | Agency | One-off | Medium | Not started
63 | Month 2 | W5 | 2026-09-20 | Reviews | Reply to every new review within two days | Cleo | Ongoing | Medium | Not started
64 | Month 2 | W5 | 2026-09-20 | Instagram | Switch to locally weighted hashtag sets, clear of prescription brand names | Agency | One-off | Medium | Not started
65 | Month 2 | W5 | 2026-09-20 | Instagram | Write alt text on every new post | Cleo | Ongoing | Medium | Not started
66 | Month 2 | W5 | 2026-09-20 | Content | Publish one reel every Wednesday | Cleo | Weekly | High | Not started
67 | Month 2 | W6 | 2026-09-27 | Website | Build the treatment pages: anti-wrinkle injections and skin boosters | Agency | One-off | High | Not started
68 | Month 2 | W6 | 2026-09-27 | Website | Internal linking pass across every page built so far | Agency | One-off | Medium | Not started
69 | Month 2 | W6 | 2026-09-27 | Website | Compress every image and write alt text across the site | Agency | One-off | Medium | Not started
70 | Month 2 | W6 | 2026-09-27 | Instagram | Reorganise Highlights by treatment | Agency | One-off | Medium | Not started
71 | Month 2 | W6 | 2026-09-27 | Ads | Build the local radius audience, 15km around Oakville | Agency | One-off | High | Not started
72 | Month 2 | W6 | 2026-09-27 | Ads | Build the 30-day engagement retargeting audience | Agency | One-off | High | Not started
73 | Month 2 | W6 | 2026-09-27 | Reviews | Check the ask against the review target and adjust it if it is lagging | Agency | Monthly | High | Not started
74 | Month 2 | W7 | 2026-10-04 | Website | Build the treatment pages: dermaplaning, electrolysis and Belkyra | Agency | One-off | High | Not started
75 | Month 2 | W7 | 2026-10-04 | Website | Build the Oakville and surrounding-area page | Agency | One-off | Medium | Not started
76 | Month 2 | W7 | 2026-10-04 | Website | Mobile speed pass | Agency | One-off | Medium | Not started
77 | Month 2 | W7 | 2026-10-04 | Ads | Export the patient list from the booking system for the lookalike audience | Cleo | One-off | Medium | Not started
78 | Month 2 | W7 | 2026-10-04 | Ads | Build the lookalike audience | Agency | One-off | Medium | Not started
79 | Month 2 | W7 | 2026-10-04 | Ads | Launch three or four ad creatives pulled from existing carousels | Agency | One-off | High | Not started
80 | Month 2 | W8 | 2026-10-11 | Website | Final content and compliance review of every page before launch | Both | One-off | High | Not started
81 | Month 2 | W8 | 2026-10-11 | Website | LAUNCH: site live, Search Console verified, sitemap submitted, analytics running | Agency | One-off | High | Not started
82 | Month 2 | W8 | 2026-10-11 | Website | Repoint the GBP website field at the live site | Agency | One-off | High | Not started
83 | Month 2 | W8 | 2026-10-11 | Citations | Update every directory listing to the new website URL | Agency | One-off | Medium | Not started
84 | Month 2 | W8 | 2026-10-11 | Instagram | Update the link in bio to the live site | Agency | One-off | High | Not started
85 | Month 2 | W8 | 2026-10-11 | Measurement | Confirm Search Console and analytics are both recording on the live domain | Agency | One-off | High | Not started
86 | Month 2 | W8 | 2026-10-11 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
87 | Month 3 | W9 | 2026-10-18 | Website | Confirm every page is indexed in Search Console and fix what is not | Agency | One-off | High | Not started
88 | Month 3 | W9 | 2026-10-18 | Website | On-page pass on the home page: title, H1, opening copy, internal links | Agency | One-off | High | Not started
89 | Month 3 | W9 | 2026-10-18 | Local links | Submit to the Oakville business directories | Agency | One-off | Medium | Not started
90 | Month 3 | W9 | 2026-10-18 | Local links | Ask Allure about a cross-link between the two businesses | Cleo | One-off | Low | Not started
91 | Month 3 | W9 | 2026-10-18 | Measurement | First post-launch read on Search Console impressions and queries | Agency | One-off | Medium | Not started
92 | Month 3 | W10 | 2026-10-25 | Website | On-page pass on the four highest-intent treatment pages | Agency | One-off | High | Not started
93 | Month 3 | W10 | 2026-10-25 | Website | Add FAQ blocks with FAQ schema to every treatment page | Agency | One-off | Medium | Not started
94 | Month 3 | W10 | 2026-10-25 | Content | Write the first question-intent article and link it to its treatment page | Agency | One-off | Medium | Not started
95 | Month 3 | W10 | 2026-10-25 | Local links | Approach Halton-area partners for mentions and links | Agency | One-off | Medium | Not started
96 | Month 3 | W10 | 2026-10-25 | Google profile | Add the weight-loss service entry to GBP ahead of the launch | Agency | One-off | Medium | Not started
97 | Month 3 | W11 | 2026-11-01 | Website | Fix whatever Search Console flags: coverage, mobile usability, core web vitals | Agency | One-off | High | Not started
98 | Month 3 | W11 | 2026-11-01 | Content | Write the second question-intent article | Agency | One-off | Medium | Not started
99 | Month 3 | W11 | 2026-11-01 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
100 | Month 3 | W11 | 2026-11-01 | Reviews | Check the ask conversion rate and rewrite the message if it is under 30 per cent | Agency | One-off | High | Not started
101 | Month 3 | W12 | 2026-11-08 | Measurement | Month three review: every number against the week-one baseline | Agency | Monthly | High | Not started
102 | Month 3 | W12 | 2026-11-08 | Measurement | Rank check on the map pack terms and the page terms | Agency | Monthly | High | Not started
103 | Month 3 | W12 | 2026-11-08 | Content | Write the third question-intent article | Agency | One-off | Medium | Not started
104 | Month 3 | W12 | 2026-11-08 | Local links | Chase every unanswered link approach | Agency | One-off | Low | Not started
105 | Month 4 | W13 | 2026-11-15 | Website | Build the weight-loss pre-launch page | Agency | One-off | Medium | Not started
106 | Month 4 | W13 | 2026-11-15 | Content | Write the fourth article from the questions you get asked in consults | Agency | One-off | Medium | Not started
107 | Month 4 | W13 | 2026-11-15 | Instagram | Review which posts drove profile visits and rebalance the calendar | Agency | Monthly | Medium | Not started
108 | Month 4 | W13 | 2026-11-15 | Google profile | Refresh the GBP photo set with new room and result photos | Both | One-off | Medium | Not started
109 | Month 4 | W14 | 2026-11-22 | Website | Expand the thin treatment pages: pricing ranges, aftercare, who it is not for | Agency | One-off | High | Not started
110 | Month 4 | W14 | 2026-11-22 | Local links | Sponsor or join one Oakville community listing or event | Cleo | One-off | Medium | Not started
111 | Month 4 | W14 | 2026-11-22 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
112 | Month 4 | W14 | 2026-11-22 | Content | Write the fifth article | Agency | One-off | Medium | Not started
113 | Month 4 | W15 | 2026-11-29 | Website | Add a before-and-after gallery page using consent-cleared photos only | Agency | One-off | Medium | Not started
114 | Month 4 | W15 | 2026-11-29 | Compliance | Compliance pass on the gallery page before it goes live | Agency | One-off | High | Not started
115 | Month 4 | W15 | 2026-11-29 | Google profile | Post the December holiday hours to GBP | Agency | One-off | Medium | Not started
116 | Month 4 | W15 | 2026-11-29 | Reviews | Holiday review push: ask every patient seen in November | Cleo | One-off | High | Not started
117 | Month 4 | W16 | 2026-12-06 | Measurement | Month four review: compare Search Console queries month on month | Agency | Monthly | High | Not started
118 | Month 4 | W16 | 2026-12-06 | Website | Internal linking pass now that the articles exist | Agency | One-off | Medium | Not started
119 | Month 4 | W16 | 2026-12-06 | Content | Write the sixth article | Agency | One-off | Medium | Not started
120 | Month 5 | W17 | 2026-12-13 | Google profile | Set the holiday opening hours on GBP for December and January | Agency | One-off | High | Not started
121 | Month 5 | W17 | 2026-12-13 | Instagram | Plan the December gift-card and holiday content | Agency | One-off | Medium | Not started
122 | Month 5 | W17 | 2026-12-13 | Website | Add a gift-card or holiday offer block to the home page | Agency | One-off | Medium | Not started
123 | Month 5 | W18 | 2026-12-20 | Ads | Holiday campaign: reallocate budget to the gift-card creative | Agency | Fortnightly | High | Not started
124 | Month 5 | W18 | 2026-12-20 | Content | Write the seventh article | Agency | One-off | Medium | Not started
125 | Month 5 | W18 | 2026-12-20 | Citations | Quarterly citation audit: confirm the NAP is still identical everywhere | Agency | One-off | Medium | Not started
126 | Month 5 | W19 | 2026-12-27 | Instagram | Reduced holiday cadence: stories only, one reel, but keep GBP posting daily | Cleo | One-off | Medium | Not started
127 | Month 5 | W19 | 2026-12-27 | Google profile | Confirm the holiday hours showing on Google are actually correct | Agency | One-off | High | Not started
128 | Month 5 | W20 | 2027-01-03 | Measurement | Year-end read: reviews, map pack positions, sessions and bookings | Agency | Monthly | High | Not started
129 | Month 5 | W20 | 2027-01-03 | Content | Plan the January content calendar | Agency | One-off | Medium | Not started
130 | Month 5 | W21 | 2027-01-10 | Website | January on-page sprint: refresh every title tag and meta description | Agency | One-off | High | Not started
131 | Month 5 | W21 | 2027-01-10 | Instagram | Back to full cadence with new-year treatment content | Cleo | One-off | High | Not started
132 | Month 5 | W21 | 2027-01-10 | Reviews | New-year review push | Cleo | One-off | High | Not started
133 | Month 5 | W21 | 2027-01-10 | Ads | Relaunch the standard campaign set after the holiday creative | Agency | Fortnightly | High | Not started
134 | Month 6 | W22 | 2027-01-17 | Website | Build the full weight-loss treatment page now the service is live | Agency | One-off | High | Not started
135 | Month 6 | W22 | 2027-01-17 | Content | Write the eighth article | Agency | One-off | Medium | Not started
136 | Month 6 | W22 | 2027-01-17 | Local links | Second round of local link approaches | Agency | One-off | Medium | Not started
137 | Month 6 | W23 | 2027-01-24 | Measurement | Full query review: find every term you rank between 5 and 15 for | Agency | One-off | High | Not started
138 | Month 6 | W23 | 2027-01-24 | Website | Optimise the pages behind those near-miss terms | Agency | One-off | High | Not started
139 | Month 6 | W23 | 2027-01-24 | Website | Content refresh on the three lowest-performing pages | Agency | One-off | Medium | Not started
140 | Month 6 | W24 | 2027-01-31 | Ads | Fortnightly ad review: kill anything below average cost per DM, reallocate | Agency | Fortnightly | High | Not started
141 | Month 6 | W24 | 2027-01-31 | Reviews | Check the review count against the six-month target | Agency | Monthly | High | Not started
142 | Month 6 | W24 | 2027-01-31 | Google profile | Refresh the GBP services list and the questions section | Agency | One-off | Medium | Not started
143 | Month 6 | W25 | 2027-02-07 | Measurement | Full review of every number against the week-one baseline | Agency | One-off | High | Not started
144 | Month 6 | W25 | 2027-02-07 | Website | Technical audit: speed, schema, broken links, redirects | Agency | One-off | High | Not started
145 | Month 6 | W25 | 2027-02-07 | Citations | Final citation audit for the engagement | Agency | One-off | Medium | Not started
146 | Month 6 | W26 | 2027-02-14 | Measurement | Write the six-month report | Agency | One-off | High | Not started
147 | Month 6 | W26 | 2027-02-14 | Measurement | Write the recommendation for the next six months | Agency | One-off | High | Not started
148 | Month 6 | W26 | 2027-02-14 | Website | Hand over the site documentation and every login | Agency | One-off | High | Not started

## Site Build
Website build timeline
Approved, full build. Real dates, not weeks-from-approval. Everything after 31 August slips one-for-one if the design sign-off slips.
When | What we do | What we need from Cleo | Status | Date done | Notes
Aug 24 - 28 | Planning and design: sitemap, page inventory, wireframes for home, contact and the treatment template, keyword-to-page map, brand kit pulled from design/brand | Registrar login, treatment list with current pricing, photos of the room, a headshot, logo files | Not started
Aug 31 | Design sign-off. This is the gate — nothing is built before it clears | Sign off the wireframes and the look, in writing | Not started
Sep 1 - 6 | BUILD STARTS. Hosting sorted, DNS pointed at the new site, platform set up, page structure scaffolded | Nothing. This week is ours | Not started
Sep 7 - 13 | Home and contact complete in staging: corrected address at L6M 0T9, real hours, booking link, LocalBusiness and Service schema, title tags and meta descriptions | Read the home page copy and approve it | Not started
Sep 14 - 27 | Treatment pages: lip filler, dermal filler and facial balancing, anti-wrinkle injections, skin boosters. Internal linking, image compression, alt text | Read the copy and confirm every claim is one you can stand behind | Not started
Sep 28 - Oct 4 | Remaining treatment pages: dermaplaning, electrolysis, Belkyra. The Oakville and surrounding-area page. Mobile speed pass | Nothing. This week is ours | Not started
Oct 5 - 11 | LAUNCH. Search Console verified, sitemap submitted, analytics running, GBP website field repointed, every citation updated to the new URL | Final sign-off before it goes live | Not started
Oct 12 - Nov 8 | Indexing and on-page. Fix whatever Search Console flags, FAQ schema on the treatment pages, the first three question-intent articles | The questions you get asked most in consults | Not started
Nov 9 - Feb 14 | Depth. Weight-loss page, before-and-after gallery, five more articles, near-miss query optimisation, technical audit, handover | Consent-cleared photos as they come, and the consult questions | Not started

## Reviews
Review tracker
Baseline 12 reviews at 5.0. Target 18 to 22 new ones across the six months, roughly one every ten days. Ask inside 24 hours or the number does not move. |  |  |  |  | Asks sent |  | Reviews landed
Date asked | Patient (initials) | How we asked | Asked by | Review received | Date received | Platform | Replied | Notes

## Citations
Citations and NAP
One name, one address, one phone number, everywhere. The postal code is L6M 0T9 — it is wrong on most of these today.
Directory | Listing URL | Claimed | Name correct | Address and postal code correct | Phone correct | Website URL current | Status | Date done | Notes
Google Business Profile | [6 empty] | Not started
Birdeye | [6 empty] | Not started
Facebook | [6 empty] | Not started
Fresha | [6 empty] | Not started
Yelp.ca | [6 empty] | Not started
Yellow Pages | [6 empty] | Not started
Apple Maps | [6 empty] | Not started
Bing Places | [6 empty] | Not started
RateMDs | [6 empty] | Not started
Canadian chamber directories | [6 empty] | Not started
Oakville Chamber of Commerce | [6 empty] | Not started
411.ca | [6 empty] | Not started
Cylex Canada | [6 empty] | Not started
Foursquare | [6 empty] | Not started
Instagram profile | [6 empty] | Not started
Booking system profile | [6 empty] | Not started
Halton business directory | [6 empty] | Not started

## GBP Posts
Google Business Profile posts
One a day, every weekday. Rotate the five types. Every post carries the booking link. Nothing here names a prescription drug. |  |  |  |  | Posts published
Date | Post type | Treatment or topic | Copy source | Image source | Booking link included | Published | Notes

## Metrics
Monthly numbers
Fill at the end of each month. Compare against the baseline column, not against last month.
What we track | Baseline (17 Aug) | Target by 14 Feb | End Sep | End Oct | End Nov | End Dec | End Jan | Mid Feb | Notes
Google reviews | 12 | 30 to 34, still at or near 5.0
Google review average | 5.0 | At or near 5.0
Calls from Google profile |  | Up on baseline every month
Direction requests from Google |  | Up on baseline every month
Google profile views |  | Up on baseline every month
GBP posts published in the month | 0 | 20 or more, every month
Map pack position: nurse injector oakville |  | Visible in the pack
Map pack position: botox oakville |  | Visible in the pack
Map pack position: lip filler oakville |  | Visible in the pack
Instagram profile visits |  | Up on baseline
Instagram link taps |  | Rising faster than profile visits
Reels published in the month | 0 | Four, one a week
DMs received | Not tracked | Tracked weekly from week 1
Consultations booked | Not tracked | Tracked weekly, attributed to source
Ad spend | Not supplied | Confirmed and split 70/20/10
Cost per DM from ads |  | Falling month on month
Website sessions | No site | From launch in October, rising month on month
Search Console impressions | No site | Rising month on month from October
Pages indexed | No site | Every page, confirmed in Search Console
Daily slot completion rate |  | 85 per cent or better

## Waiting On Cleo
Waiting on Cleo
Access, assets and answers. Most delay in work like this comes from waiting on these. The top four are what the build waits on.
Type | What we need | Needed by | Why it blocks us | Status | Date received | Notes
Access | Google Business Profile, and which email holds it | 2026-08-21 | Nothing on the profile can start until this is settled | Not started
Answer | Real opening hours for every day | 2026-08-21 | The hours on Google are wrong until we have these | Not started
Asset | Treatment list with current pricing | 2026-08-26 | Sitemap, service pages and the GBP services list all key off it | Not started
Access | Domain registrar login for luxurybeautybycleo.ca | 2026-08-28 | DNS has to be pointed before the build can start on 1 September | Not started
Answer | DESIGN SIGN-OFF on the wireframes and the look | 2026-08-31 | The build gate. Everything after it slips one-for-one | Not started
Asset | Photos of the treatment room and the space | 2026-08-28 | GBP photos and every website page | Not started
Asset | A current headshot | 2026-08-28 | GBP, Instagram and the site | Not started
Asset | Logo files and any brand assets you already have | 2026-08-28 | The design cannot be finalised without them | Not started
Asset | Signed before-and-after consent form | 2026-09-06 | Determines what we are allowed to publish anywhere | Not started
Access | Meta Business account and ad account | 2026-09-20 | Needed to build audiences and run ads | Not started
Access | Instagram collaborator invitation | 2026-08-28 | Needed to fix the name field, bio and link | Not started
Access | Booking system login | 2026-09-06 | Needed for the booking link and the lookalike audience | Not started
Answer | Whether Allure allows your own signage and suite designation | 2026-08-23 | Decides how we build the Google listing | Not started
Answer | The three competitors you want to be measured against | 2026-08-23 | Shapes what we track and benchmark | Not started
Answer | Your ideal patient, in your own words | 2026-09-13 | Ad audiences and page copy | Not started
Answer | Current monthly spend on Instagram and Google ads | 2026-09-13 | Cannot recommend a budget without it | Not started
Answer | Approval of the home page copy | 2026-09-13 | Home and contact cannot go into staging without it | Not started
Answer | Approval of the treatment page copy | 2026-09-27 | Every claim has to be one you can stand behind | Not started
Answer | The questions you get asked most in consults | 2026-10-18 | The articles are written from them, not invented | Not started
Answer | Commitment to the daily routine | 2026-08-21 | Five slots a day. Without them the rest of the plan does not compound | Not started